## Index
Summary
Date | 2014-05-23
Track | Application Support
Created by | Ricky Sahota
Release Date | 2014-05-23
Release Number | 2.04.02.001
Location of EAR | /local1/atg/weblogic/application/bbb_prod/BBBStore.ear /local1/atg/weblogic/application/bbb_pub/BBBStore.ear /local1/atg/weblogic/application/bbb_stg/BBBStore.ear
Reviewed by | Imran Ali
Scope | JIRA Defects [Desktop Baby, Desktop BBB, Desktop Canada, Mobile Baby, Mobile BBB and Mobile Canada]
Prerequisite | May build - 2.04.01.001 (R2.2) must have been applied. Also previous build packets for 2.04.02.001 should be applied
(Steady)
(Steady)
(Steady)
(Steady)
(Steady)
(Steady)
(Steady)
(Steady)
(Steady)
(Steady)
(Steady)
(Steady)

## Additonal Items (hidden)
December 7th Release
New dropdown taxonomy markup/CSS | Mandeep/Vijay
Seller registration number | Rajesh
- Keyboard Focus Indication All links have no focus indication because of "outline: 0 none;" Suggestion is to use same effect for hover as for focus (active) | Mandeep
Disable Inventory tab in BCC for QA and Production environments
Secure Cookie

## Desktop Defects
May 23 Release
Defect # | Priority | Summary | Resolution Status | Regression Areas | QA Status | comment
BBBSL-2556 | Severity/Priority 1 | Fw: FYI: Changes in Navigation Links | Resolved | Please check the SEO URLs of L1 , L2 and L3 categories and they should be in lower case | Not validated | This was applied to production as hot fix on 16 May but It needs to be validated in this build
BBBSL-2668 | Severity/Priority 1 | Found a "Gift Options" page after shipping page for BOPUS orders | Resolved | For BOPUS orders, gifting page should not appear | Not validated | This was applied to production as hot fix on 16 May but It needs to be validated in this build
PS-21781 | Severity/Priority 1 | CSR tool not working | Resolved | Please check whether CSR Tool is working or not 2) Log Messages captured in Process_Support table. 3) Guided Selling Endeca Baseline working fine. | Not validated | This was applied to production as hot fix on 16 May and it is currently closed but It needs to be validated in this build
BBBSL-2699 | Severity/Priority 1 | CSS not rendering energy guides or lighting facts icons | Resolved | PDP | Passed | Tested on 5/19
BBBSL-2340 | Severity/Priority 2 | Remove temporary tables from Endeca stored procedures | Resolved | Performance improvement in Endeca feed files generation, now they should take less time | Not validated | This was applied to production as hot fix on 16 May but It needs to be validated in this build
PS-18625 | Severity/Priority 3 | Check Out - Multi Ship: Gift Wrap | Resolved | Regression areas are for both anonymous & logged in user : 1. Single shipping checkout (with gift message checkbox enabled & disabled). 2. Multi shipping checkout (with gift message checkbox enabled & disabled). 3. Express Checkout. 4. Checking of gift message info in the order xml. | Not validated | This was applied to production as hot fix on 16 May but It needs to be validated in this build
PS-18958 | Severity/Priority 3 | Manage Registry - Quantity Field has Hidden Spinner Controls | Resolved | Logged-in user>View/Manage registry page | Passed | Tested on box 27 on 5/23
BBBSL-2695 | Severity/Priority 3 | My Account Overview - Favorite Store - Change store link should to Store locator | Resolved | Logged-in user>My Account-page>Favorite store widget & Logged-in user>Favorite store page | Passed | Tested on box 27 on 5/22

## Mobile Defects
May 23 Release
Defect # | Priority | Title | Status | Regression Areas | QA Status | Comments
BSL-2469 | Severity/Priority 2 | Autoselect CC (m43/RM-18960) | Resolved | Credit Card Section(Payment Section,Add New Card) | Not validated
BSL-2579 | Severity/Priority 2 | On Canada Mobile>Logged-in user>checkout>Shipping page ,there is no option to add new address | Resolved | Logged-in user>Checkout>Shipping page , Checkout flow | Passed | Tested on box 27 on 5/22
BSL-2581 | Severity/Priority 2 | Firefox-29 : User is not able to enter "Credit Card" Details & hence not able to proceed in checkout Flow. | Resolved | Checkout>Payment page, Checkout flow | Passed | Tested on box 27 on 5/22
BSL-2418 | Severity/Priority 2 | Error, Displaying "did you mean..." on BBBY & Baby Mobile Site Search | Resolved | Search results page, | Passed | Tested on box 27 on 5/22
BSL-2601 | Severity/Priority 3 | "Find in Store" from Registry List is displaying inline error message when "Use My Current Location" is selected | Resolved | Find-Store-page | Passed | Tested on box 27 on 5/22
BSL-2521 | Severity/Priority 4 | Ok button not responsive on estimated shipping modal in UAT East & Production | Resolved | Shipping Modal on Cart page | Passed | Tested on box 27 on 5/23
BSL-2395 | Severity/Priority 4 | UI is distorted when user search “Convertible Car Seat” option in "search" Page. | Resolved | Search results page | Passed | Tested on box 27 on 5/23

## Known Issues
May 23 Release
JIRA Defect ID | Priority | Issue Description | Impacted Area | Comments