## Index
Summary
Date | 2014-05-30
Track | Application Support
Created by | Madhur Aggarwal
Release Date | 2014-05-30
Release Number | 2.04.02.001
Location of EAR | /local1/atg/weblogic/application/bbb_prod/BBBStore.ear /local1/atg/weblogic/application/bbb_pub/BBBStore.ear /local1/atg/weblogic/application/bbb_stg/BBBStore.ear
Reviewed by | Imran Ali
Scope | JIRA Defects [Desktop Baby, Desktop BBB, Desktop Canada, Mobile Baby, Mobile BBB and Mobile Canada]
Prerequisite | May build - 2.04.01.001 (R2.2) must have been applied. Also previous build packets for 2.04.02.001 should be applied
(Steady)
(Steady)
(Steady)
(Steady)
(Steady)
(Steady)
(Steady)
(Steady)
(Steady)
(Steady)
(Steady)
(Steady)

## Additonal Items (hidden)
December 7th Release
New dropdown taxonomy markup/CSS | Mandeep/Vijay
Seller registration number | Rajesh
- Keyboard Focus Indication All links have no focus indication because of "outline: 0 none;" Suggestion is to use same effect for hover as for focus (active) | Mandeep
Disable Inventory tab in BCC for QA and Production environments
Secure Cookie

## Desktop Defects
May 30 Release
Defect # | Priority | Summary | Resolution Status | Regression Areas | QA Status | Comments
BBBSL-2636 | Severity/Priority 2 | Synchronizing order object for update | Resolved | 1.While placing the order, checking the contents of the checkout_confirmation page, review cart, order xml & order confirmation email which should be the same & contains correct info for both Mobile & Desktop. 2. Submission of orders to tibco on running BBBTibcoOrderMessageSchedulerJob. Also check the sub status in DB in BBB_ORDER table for those orders. | Passed | Fixed as part of May/ June Release
BBBSL-2734 | Severity/Priority 2 | Implement Point #1 of BBBSL-2636 | Resolved | Pricing Webservice | Passed | Fixed as part of May/ June Release
BBBSL-2735 | Severity/Priority 2 | Implement Point #2, #3, #12, #14 of BBBSL-2636 | Resolved | 1. Merging of order after login.(Add to registry an item, save for later an item as guest user & then log in into an account already containing the items) 2. Login, change password, forgot password during Checkout flow. 3. Account management(change, forgot password, account extension, login) during normal flow. 4. Facebook log in/ auto log in during checkout & through login page. 5. Save for later from PDP page. Save for later then add to cart items on cart page. 6. Account extension from a sister site after placing an order on checkout confirmation page & checking order history. | Passed | Fixed as part of May/ June Release
PS-21422 | Severity/Priority 2 | Store 439 Preferred Store Assignment | Resolved | 1. Preferred store id during registry Creation on Mobile & Desktop. 2. Preferred store id during Registry update on Mobile & Desktop. | Passed | Fixed as part of May/ June Release
BBBSL-2218 | Severity/Priority 2 | Touch enabled the homepage hero for tablets | Resolved | Hero spot on iPAD | Not Verified
PS-19401 | Severity/Priority 2 | Please send .jsp page equivalents for friendly SEO URL | Resolved | NA | Dev Testable
BBBSL-2751 | Severity/Priority 3 | Refactor the code to update sales channel using OOB component. | Resolved | 1. Placing an order from Mobile, Desktop & Mobile App & checking the sales channel in order xml. | Passed | Fixed as part of May/ June Release
BBBSL-2691 | Severity/Priority 3 | Learn More link in college fly out under college registry goes to My Account in the mentioned flow | Resolved | 1. Shop for college flyout. 2. Find my college and college registry in registry flyout | Not Verified

## Mobile Defects
May 30 Release
Defect # | Priority | Title | Resolution Status | Regression Areas | QA Status | Comments
BSL-2573 | Severity/Priority 2 | getAllValuesForKey should throw BusinessException instead of 500 errors. | Resolved | 1) Check for Config keys getting populated from database. 2) Check for Config keys getting cached for mobile. 3) Checking mobile and desktop server logs. 4) Basic sanity on all the three mobile sites. | Not Verified
BSL-2585 | Severity/Priority 4 | Supress 500 error code in case of searchSKUInStore service. | Resolved | 1) Check for Pickup in store for desktop and mobile sites. 2) Checking mobile and desktop server logs. 3) checkout using bopus Order for mobile and desktop logs | Not Verified

## Known Issues
May 30 Release
JIRA Defect ID | Priority | Issue Description | Impacted Area | Comments