## Index
Summary
Date | 2014-11-03
Track | Application Support
Created by | Ishu Mehta
Release Date | 2014-11-03
Release Number | 2.05.02.001
Location of EAR | /local1/atg/weblogic/application/bbb_prod/BBBStore.ear /local1/atg/weblogic/application/bbb_pub/BBBStore.ear /local1/atg/weblogic/application/bbb_stg/BBBStore.ear
Reviewed by
Scope | JIRA Defects [Desktop Baby, Desktop BBB, Desktop Canada, Mobile Baby, Mobile BBB and Mobile Canada]
Prerequisite | JAN PS build packets (2.05.02.001) must have been applied to environment before this packet.
(Steady)
(Steady)
(Steady)
(Steady)
(Steady)
(Steady)
(Steady)
(Steady)
(Steady)
(Steady)
(Steady)
(Steady)

## Additonal Items (hidden)
December 7th Release
New dropdown taxonomy markup/CSS | Mandeep/Vijay
Seller registration number | Rajesh
- Keyboard Focus Indication All links have no focus indication because of "outline: 0 none;" Suggestion is to use same effect for hover as for focus (active) | Mandeep
Disable Inventory tab in BCC for QA and Production environments
Secure Cookie

## Desktop Defects
JAN PS ¦ Sprint 3- Build 1¦ 03- Nov
Defect # | Priority | Summary | Resolution Status | Regression Areas | QA Status | Comments
PS-20926 | Severity/Priority 1 | Rename "More" upon refresh | Resolved | L1 Navigation Menu | Pass
BBBSL-2683 | Severity/Priority 1 | Certona component placement on order confirmation email | Resolved | Order Confirmation UI | Not Tested
BBBSL-3000 | Severity/Priority 1 | Certona - add to registry tagging | Resolved | Verify the <Div></Div> tag for each certona carousals | Not Tested
PS-22917 | Severity/Priority 1 | Find Your College Mapquest Results | Resolved | Store Availability Functionality at Find Your College Page. | Not Tested
PS-23894 | Severity/Priority 1 | Pack and Hold Option On The Live Site | Resolved | The Pack and Hold option should be present if the Product has been added from Qucik view | Pass
BBBSL-3425 | Severity/Priority 2 | Adding Instagram and Twitter icon to Baby web, mobile, app | Resolved | Footer on desktop, Mobile Web, Mobile App. | Not Tested
BBBSL-3035 | Severity/Priority 2 | Incorrect Campaign IDs are getting assigned | Resolved | Bazaar Voice Functionality Testing | Pass | This defect is purely dev testable.
BBBSL-2901 | Severity/Priority 2 | Quantity Buttons on PDP - Wrapping on multisku prices | Resolved | PDP Page for all concepts | Pass
BBBSL-3255 | Severity/Priority 2 | UE SOD ¦ BABY-Reviews are yellow- Should be pink as on the PDP | Resolved | PLP page Baby site only | Pass

## Mobile Defects
JAN PS ¦ Sprint 3- Build 1¦ 03- Nov
Defect # | Priority | Title | Status | Regression Areas | QA Status | Comments
BSL-2817 | Severity/Priority 1 | Certona - for mobile, we are not sending them the correct order id | Resolved | Third Party calls on mobile Order Confirmation Page. | Not Tested
BSL-2613 | Severity/Priority 1 | Omniture - need to maintain the query string papameters when doing a redirect | Resolved | Mobile Redirect for Category and Brand Pages | Pass
BSL-2770 | Severity/Priority 1 | Omniture - revenues in Omniture is before markdowns and it should be after | Resolved | Checkout confirmation page | Pass
BSL-2821 | Severity/Priority 1 | Shop by Brand on mobile slider "7" is wrapping | Resolved | Brand Listing Page – AlphaNumeric Navigation Width | Pass
BSL-2819 | Severity/Priority 2 | Email opt-in for Guest Checkout for Mobile | Resolved | Billing page for mobile | Pass
BSL-2794 | Severity/Priority 2 | Prod APP: Emailing registry to a friend shows an error. | Resolved | Email Registry on all mobile concepts | Not Tested

## Known Issues
JAN PS ¦ Sprint 3- Build 1¦ 03- Nov
JIRA Defect ID | Priority | Issue Description | Impacted Area | Comments