## Index
Summary
Date | 2014-07-11
Track | Application Support
Created by | Antariksh Tiwary
Release Date | 2014-07-11
Release Number | 2.05.02.001
Location of EAR | /local1/atg/weblogic/application/bbb_prod/BBBStore.ear /local1/atg/weblogic/application/bbb_pub/BBBStore.ear /local1/atg/weblogic/application/bbb_stg/BBBStore.ear
Reviewed by | Manuj Gupta
Scope | JIRA Defects [Desktop Baby, Desktop BBB, Desktop Canada, Mobile Baby, Mobile BBB and Mobile Canada]
Prerequisite | Oct build packets (2.05.01.001) must have been applied to environment before this packet.
(Steady)
(Steady)
(Steady)
(Steady)
(Steady)
(Steady)
(Steady)
(Steady)
(Steady)
(Steady)
(Steady)
(Steady)

## Additonal Items (hidden)
December 7th Release
New dropdown taxonomy markup/CSS | Mandeep/Vijay
Seller registration number | Rajesh
- Keyboard Focus Indication All links have no focus indication because of "outline: 0 none;" Suggestion is to use same effect for hover as for focus (active) | Mandeep
Disable Inventory tab in BCC for QA and Production environments
Secure Cookie

## Desktop Defects
NOV 07 Release
Defect # | Priority | Summary | Resolution Status | Regression Areas | QA Status | Comments
BBBSL-3394 | Priority 1 | Shop Collection Link Broken, Image Not Available on PDP | Unresolved | check the "email a friend" functionality for all kind of products.Also please check that other emails are working fine , e.g:- email a cart , email registry etc
BBBSL-3173 | Priority 1 | Coupons - show expiration | Unresolved | Check page where coupon is displayed like account and cart page for logged in user.Coupon page after billing page for both anonymous and logged in user.
BBBSL-3522 | Priority 1 | BBBSL-3318 Retry CyberSource tax calls | Unresolved | Cyber Souce Tax Calculation. Order XML with TAX details
BBBSL-2683 | Priority 1 | Certona component placement on order | Unresolved | Order Email UI
BBBSL-3291 | Priority 1 | Certona - implement code to capture quick views | Unresolved | PDP and PLP Certona Data collection calls. QuickView Certona Data collection calls.
PS-25363 | Priority 2 | Incorrect image SKU # 43100361, Dept 874 | Unresolved | PDP
PS-22705 | Priority 1 | Order Status coming as F for Legacy Orders | Unresolved | Order Status for Legacy order on track order page
BBBSL-3635 | Priority 2 | PayPal orders with null address verified status is failing | Unresolved | Order xml in case of PayPal Orders |  | Was sent as patch on top of Oct Release.
BBBSL-2432 | Priority 1 | PDP CTA Messaging | Invalid
BBBSL-2782 | Priority 1 | YourAmigo data feed - remove brand names from merchandise field and include "TM"/"R" symbols for brands | Invalid
BBBSL-3576 | Priority 1 | BazaarVoice Review was not getting updated on SD | Unresolved | Regression Area: Reviews on PDP and PLP |  | Was sent as patch on top of Oct Release.
BBBSL-3444 | Priority 1 | RKG Display Floodlight Tags for Baby.com Registry Section | Unresolved | RKG tags fired on Registry pages and other pages
BBBSL-2530 | Priority 1 | RKG Display Floodlight Tag Additons for BBB Registry Pages 1.24.14 | Unresolved | RKG tags fired on Registry pages and other pages
PS-25621 | Priority 2 | Search Button wraps on Registry Landing Page | Unresolved | registry flyout |  | Was sent as patch on top of Oct Release.

## Mobile Defects
NOV 07 Release
Defect # | Priority | Title | Status | Regression Areas | QA Status | Comments
BSL-2667 | Priority 1 | Internal Server Error occur due to the Wrong Credit Card CVV number ( after 2 attempts ) | Unresolved | Credit Card Validation on payment & preview Page. Credit Card Attempts failure calls
BSL-2802 | Priority 1 | buybuy Baby Mobile Accessibility Issues | Unresolved | Mobile Site Accessibility
BSL-2801 | Priority 1 | Mobile Accessibility Issues | Unresolved | Mobile Site Accessibility
BSL-2669 | Priority 2 | $50 Bonus Gift Card link not working on gifter view | Unresolved | Registry Gifter view
BSL-2798 | Priority 2 | Items not being added to active registry | Invalid

## Known Issues
Nov 07 Release
JIRA Defect ID | Priority | Issue Description | Impacted Area | Comments