## Index
Summary
Date | 2014-10-10
Track | Application Support
Created by | Ayush Gupta
Release Date | 2014-10-10
Release Number | 2.05.02.001
Location of EAR | /local1/atg/weblogic/application/bbb_prod/BBBStore.ear /local1/atg/weblogic/application/bbb_pub/BBBStore.ear /local1/atg/weblogic/application/bbb_stg/BBBStore.ear
Reviewed by | Minhajul
Scope | JIRA Defects [Desktop Baby, Desktop BBB, Desktop Canada, Mobile Baby, Mobile BBB and Mobile Canada]
Prerequisite | August build packets (2.04.03.001) must have been applied to environment before this packet.
(Steady)
(Steady)
(Steady)
(Steady)
(Steady)
(Steady)
(Steady)
(Steady)
(Steady)
(Steady)
(Steady)
(Steady)

## Additonal Items (hidden)
December 7th Release
New dropdown taxonomy markup/CSS | Mandeep/Vijay
Seller registration number | Rajesh
- Keyboard Focus Indication All links have no focus indication because of "outline: 0 none;" Suggestion is to use same effect for hover as for focus (active) | Mandeep
Disable Inventory tab in BCC for QA and Production environments
Secure Cookie

## Desktop Defects
OCT 10 Release
Defect # | Priority | Summary | Resolution Status | Regression Areas | QA Status | Comments
BBBSL-2720 | Severity/Priority 1 | Omniture - event 35 does not fire after the build on 05/15/14 | Fixed | Add to Wish List on cart page, PDP page, Product Comparison, Quick View
PS-20925 | Severity/Priority 1 | "back to top" button on manage registry | Fixed | Mange Registry Page
BBBSL-2400 | Severity/Priority 1 | Please remove "nofollow" from L3 navigation links living under "Bed & Bath" L1 | Fixed | Category Navigation links, PLP and Search results page facets
BBBSL-3147 | Severity/Priority 2 | Desk-evar46 value not being fired right for Collections | Open | Omniture call for PDP pages and Quick view
BBBSL-2358 | Severity/Priority 2 | greater sign spacing at L2 | Open | Could not Reproduce

## Mobile Defects
OCT 10 Release
Defect # | Priority | Title | Status | Regression Areas | QA Status | Comments
BSL-2672 | Severity/Priority 2 | BBBY CA - Find My College search returns HTTP 500 error | Fixed | Find My College Functionality at both Desktop and Mobile.

## Known Issues
OCT 10 Release
JIRA Defect ID | Priority | Issue Description | Impacted Area | Comments