## Index
Summary
Date | 29/10/2014
Track | Application Support
Created by | Chetan kapoor
Release Date | 29/10/2014
Release Number | 2.05.02.001
Location of EAR | /local1/atg/weblogic/application/bbb_prod/BBBStore.ear /local1/atg/weblogic/application/bbb_pub/BBBStore.ear /local1/atg/weblogic/application/bbb_stg/BBBStore.ear
Reviewed by
Scope | JIRA Defects [Desktop Baby, Desktop BBB, Desktop Canada, Mobile Baby, Mobile BBB and Mobile Canada]
Prerequisite | JAN PS build packets (2.05.02.001) must have been applied to environment before this packet.
(Steady)
(Steady)
(Steady)
(Steady)
(Steady)
(Steady)
(Steady)
(Steady)
(Steady)
(Steady)
(Steady)
(Steady)

## Additonal Items (hidden)
December 7th Release
New dropdown taxonomy markup/CSS | Mandeep/Vijay
Seller registration number | Rajesh
- Keyboard Focus Indication All links have no focus indication because of "outline: 0 none;" Suggestion is to use same effect for hover as for focus (active) | Mandeep
Disable Inventory tab in BCC for QA and Production environments
Secure Cookie

## Desktop Defects
JAN PS ¦ Sprint 2- Build 1¦ 20- Oct
Defect # | Priority | Summary | Resolution Status | Regression Areas | QA Status | Comments
BBBSL-3068 | P1 | Certona - we need to add the product URL in the product feeds to Certona | Available at QA Box. | Certona Feed file generation for both Partial and Full scenarios.
BBBSL-2325 | P1 | Special characters in product name - BV feed | Available at QA Box. | Bazaar Voice Feed file generation for both Partial and Full scenarios.
BBBSL-3216 | P1 | Omniture International shipping - full tagging | Code fix already done in LTL | Whole site links related to international shipping
PS-24981 | Severity/Priority 4 | File Upload - Countdown Files - Oct 10, 2014 ¦ Commit files to Proper Branches |  | Business handles this folder.
BBBSL-3200 | Severity/Priority 1 | Omniture - corrections/enhancements to cart variables | Open | Omniture tagging for Mobile and Desktop around checkout flow
BBBSL-2986 | Severity/Priority 2 | Problems with iName field in RKG Order Pixel | Open | iName in RKG Order Pixel

## Mobile Defects
JAN PS ¦ Sprint 2- Build 1¦ 20- Oct
Defect # | Priority | Title | Status | Regression Areas | QA Status | Comments

## Known Issues
JAN PS ¦ Sprint 2- Build 1¦ 20- Oct
JIRA Defect ID | Priority | Issue Description | Impacted Area | Comments