## Index
Summary
Date | 27/10/2014
Track | Application Support
Created by | Manuj Gupta
Release Date | 27/10/2014
Release Number | 2.05.02.001
Location of EAR | /local1/atg/weblogic/application/bbb_prod/BBBStore.ear /local1/atg/weblogic/application/bbb_pub/BBBStore.ear /local1/atg/weblogic/application/bbb_stg/BBBStore.ear
Reviewed by
Scope | JIRA Defects [Desktop Baby, Desktop BBB, Desktop Canada, Mobile Baby, Mobile BBB and Mobile Canada]
Prerequisite | JAN PS build packets (2.05.02.001) must have been applied to environment before this packet.
(Steady)
(Steady)
(Steady)
(Steady)
(Steady)
(Steady)
(Steady)
(Steady)
(Steady)
(Steady)
(Steady)
(Steady)

## Additonal Items (hidden)
December 7th Release
New dropdown taxonomy markup/CSS | Mandeep/Vijay
Seller registration number | Rajesh
- Keyboard Focus Indication All links have no focus indication because of "outline: 0 none;" Suggestion is to use same effect for hover as for focus (active) | Mandeep
Disable Inventory tab in BCC for QA and Production environments
Secure Cookie

## Desktop Defects
JAN PS ¦ Sprint 2- Build 2¦ 27- Oct
Defect # | Priority | Summary | Resolution Status | Regression Areas | QA Status | Comments
BBBSL-3393 | Severity/Priority 1 | Please edit the size field on the MSWP PDP to function the same way as Quick View on the collection 215670 PDP | Fixed | PDP, Collection Pages |  | It’s adhoc task
PS-24573 | Severity/Priority 1 | Omniture - capture quick view as prodview to support browse abandon | None | Omniture calls
BBBSL-2817 | Severity/Priority 1 | Omniture - find in store on collection page fires wrong id | None | Omniture call in quick view modal
BBBSL-3091 | Severity/Priority 1 | SEO issue: Titles and meta-descriptions changed for all category pages | Fixed | PIM Feeds
BBBSL-3297 | Severity/Priority 1 | 500 Internal Server Error, oops page during login process when not able to load associated registry | Fixed
BBBSL-3000 | Severity/Priority 1 | Certona - tagging | Fixed | All those pages where Certona schemes and the products from Certona are visible , i.e, homepage , Cart , top registry items etc etc.
BBBSL-2628 | Severity/Priority 1 | Omniture - no tagging fires when adding items to registry from top registry items container | Fixed | Omniture testing while adding items from top registry items
BBBSL-2465 | Severity/Priority 2 | New Nodes SEO Copy flow to Production | Fixed | PIM Feeds
BBBSL-3147 | Severity/Priority 2 | Desk-evar46 value not being fired right for Collections | Fixed

## Mobile Defects
JAN PS ¦ Sprint 2- Build 2¦ 27- Oct
Defect # | Priority | Title | Status | Regression Areas | QA Status | Comments
BSL-2623 | Severity/Priority 2 | Mobile ¦ Security error has occurred on session time out while updating personal information | CNR | Mobile Security

## Known Issues
JAN PS ¦ Sprint 2- Build 2¦ 27- Oct
JIRA Defect ID | Priority | Issue Description | Impacted Area | Comments