## Index
Summary
Date | 23/1/2015
Track | Application Support
Created by | Neeraj Uttreja
Release Date | 23/1/2015
Release Number | 2.05.03.001
Location of EAR | /local1/atg/weblogic/application/bbb_prod/BBBStore.ear /local1/atg/weblogic/application/bbb_pub/BBBStore.ear /local1/atg/weblogic/application/bbb_stg/BBBStore.ear
Reviewed by | Antariksh Tiwary
Scope | JIRA Defects [Desktop Baby, Desktop BBB, Desktop Canada, Mobile Baby, Mobile BBB and Mobile Canada]
Prerequisite
(Steady)
(Steady)
(Steady)
(Steady)
(Steady)
(Steady)
(Steady)
(Steady)
(Steady)
(Steady)
(Steady)
(Steady)

## Additonal Items (hidden)
December 7th Release
New dropdown taxonomy markup/CSS | Mandeep/Vijay
Seller registration number | Rajesh
- Keyboard Focus Indication All links have no focus indication because of "outline: 0 none;" Suggestion is to use same effect for hover as for focus (active) | Mandeep
Disable Inventory tab in BCC for QA and Production environments
Secure Cookie

## Desktop Defects
JAN 23 Release
Defect # | Priority | Summary | Resolution Status | Regression Areas | QA Status | Comments
BBBSL-4181 | Severity/Priority 2 | Intl Shipping: Cart Error Messaging | Resolved | Error Messaging on Cart Page | Not Tested
BBBSL-4071 | Severity/Priority 2 | Omniture feed enhancement if a product has no L1/L2/L3 | Resolved | Omniture Product Feeds | Not Tested
BBBSL-4068 | Severity/Priority 2 | Related search links | Resolved | Home Page and Category Landing Page | Not Tested
BBBSL-3466 | Severity/Priority 2 | Omniture - cart analyzer is not firing evar1 | Resolved | Omniture event on Add to cart from Cart Analyzer | Not Tested
BBBSL-3203 | Severity/Priority 2 | Omniture - products missing proper tagging are growing | Resolved | Omniture Prop2 and Prop3 values on PDP page | Not Tested
BBBSL-2628 | Severity/Priority 2 | Omniture - no tagging fires when adding items to registry from top registry items container | Resolved | Omniture event on clicking "Add to Registry" from Top registry items container | Not Tested
BBBSL-3451 | Severity/Priority 2 | Business control of Scene 7 Zoom by category | Resolved | PDP Page | Not Tested

## Mobile Defects
JAN 23 Release
Defect # | Priority | Title | Status | Regression Areas | QA Status | Comments
BSL-3154 | Severity/Priority 2 | Collection URL issue - High Priority for Registry Howbook (Jan Release) | Resolved | PDP pages for Collection, Accessory and MultiSKU Products | Not Tested
BSL-3068 | Severity/Priority 2 | Omniture - mbaby.com out of stock tagging is inconsistant, causing higher out of stock numbers | Resolved | NA | Not Tested

## Known Issues
JAN 23 Release
JIRA Defect ID | Priority | Issue Description | Impacted Area | Comments
Registry and Coupoun Servies are down.