## Index
Summary
Date | 27/2/2015
Track | Application Support
Created by | Virender Sundriyal
Release Date | 27/2/2015
Release Number | 2.05.03.001
Location of EAR | /local1/atg/weblogic/application/bbb_prod/BBBStore.ear /local1/atg/weblogic/application/bbb_pub/BBBStore.ear /local1/atg/weblogic/application/bbb_stg/BBBStore.ear
Reviewed by | Rishabh Garg
Scope | JIRA Defects [Desktop Baby, Desktop BBB, Desktop Canada, Mobile Baby, Mobile BBB and Mobile Canada]
Prerequisite | Jan PS must be deployed
(Steady)
(Steady)
(Steady)
(Steady)
(Steady)
(Steady)
(Steady)
(Steady)
(Steady)
(Steady)
(Steady)
(Steady)

## Additonal Items (hidden)
December 7th Release
New dropdown taxonomy markup/CSS | Mandeep/Vijay
Seller registration number | Rajesh
- Keyboard Focus Indication All links have no focus indication because of "outline: 0 none;" Suggestion is to use same effect for hover as for focus (active) | Mandeep
Disable Inventory tab in BCC for QA and Production environments
Secure Cookie

## Desktop Defects
FEB 27 Release
Defect # | Priority | Summary | Resolution Status | Regression Areas | QA Status | Comments
BBBSL-4684 | Severity/Priority 1 | Omniture/Certona - send product id's in WS call to Certona from order confirmation email | Resolved | Order Confirmation Email
BBBSL-4055 | Severity/Priority 2 | Omniture - Add to Wish List | Resolved | add to wish list from PDP and quick view functionality is working fine for anonymous and logged in user
PS-29391 | Severity/Priority 2 | Personal Page: Low Res images on IE | Resolved | NA

## Mobile Defects
FEB 27 Release
Defect # | Priority | Title | Resolution Status | Regression Areas | QA Status | Comments
BSL-3154 | Severity/Priority 2 | Collection URL issue - High Priority for Registry Howbook (Jan Release) | Resolved | Mobile Web/App PDP pages for Collection, Accessory and MultiSKU Products
BSL-3068 | Severity/Priority 2 | Omniture - mbaby.com out of stock tagging is inconsistant, causing higher out of stock numbers | Resolved | Omniture call on PDP
BSL-2772 | Severity/Priority 2 | Mobile Sort by Option does not adjust URL | Resolved | Mobile ProductListing Page and search page

## Known Issues
DEC 05 Release
JIRA Defect ID | Priority | Issue Description | Impacted Area | Comments