## Index
Summary
Date | 14/4/2015
Track | Application Support
Created by | Neeraj Uttreja
Release Date | 14/4/2015
Release Number | 2.05.04.001
Location of EAR | /local1/atg/weblogic/application/bbb_prod/BBBStore.ear /local1/atg/weblogic/application/bbb_pub/BBBStore.ear /local1/atg/weblogic/application/bbb_stg/BBBStore.ear
Reviewed by | Antariksh Tiwary
Scope | JIRA Defects [Desktop Baby, Desktop BBB, Desktop Canada, Mobile Baby, Mobile BBB and Mobile Canada]
Prerequisite | Feb PS must be deployed
(Steady)
(Steady)
(Steady)
(Steady)
(Steady)
(Steady)
(Steady)
(Steady)
(Steady)
(Steady)
(Steady)
(Steady)

## Additonal Items (hidden)
December 7th Release
New dropdown taxonomy markup/CSS | Mandeep/Vijay
Seller registration number | Rajesh
- Keyboard Focus Indication All links have no focus indication because of "outline: 0 none;" Suggestion is to use same effect for hover as for focus (active) | Mandeep
Disable Inventory tab in BCC for QA and Production environments
Secure Cookie

## Desktop Defects
April 14 Release
Defect # | Priority | Summary | Resolution Status | Regression Areas | QA Status | Comments
BBBSL-5249 | Severity/Priority 1 | No Top Navigation on Canada | Resolved | NA | Not Tested
BBBSL-4906 | Severity/Priority 2 | Bellatrix - Search within Department | Resolved | Number of results coming in the type ahead for different buckets for Desktop and mobile. | Not Tested
BBBSL-4759 | Severity/Priority 2 | Facebook API Update for FB Connect | Resolved | FB login and create account functionality for Desktop site | Not Tested
BBBSL-4324 | Severity/Priority 2 | Omniture - track units and rev added to cart | Resolved | Pages/Sections from where we can add product to cart | Not Tested
BBBSL-4170 | Severity/Priority 2 | "Email Confirmation" mail, the some of the "Days & Hours" are not displaying correctly. | Resolved | Order Confirmation Email, Order detail page layout | Not Tested
BBBSL-4065 | Severity/Priority 2 | Pack and hold lable is missing after adding the Product in registry and from registry to cart. | Resolved | Add to cart from all locations including registry, pdp, quick view in both mobile and desktop | Not Tested
AC-53 | Severity/Priority 3 | Accessibility 3.2 | Resolved | Shop our Brands | Not Tested

## Mobile Defects
April 14 Release
Defect # | Priority | Title | Resolution Status | Regression Areas | QA Status | Comments

## Known Issues
April 14 Release
JIRA Defect ID | Priority | Issue Description | Impacted Area | Comments