## Index
Summary
Date | 28/4/2015
Track | Application Support
Created by | Neeraj Uttreja
Release Date | 28/4/2015
Release Number | 2.06.01.001
Location of EAR | /local1/atg/weblogic/application/bbb_prod/BBBStore.ear /local1/atg/weblogic/application/bbb_pub/BBBStore.ear /local1/atg/weblogic/application/bbb_stg/BBBStore.ear
Reviewed by | Jatin Suri
Scope | JIRA Defects [Desktop Baby, Desktop BBB, Desktop Canada, Mobile Baby, Mobile BBB and Mobile Canada]
Prerequisite | April PS must be deployed
(Steady)
(Steady)
(Steady)
(Steady)
(Steady)
(Steady)
(Steady)
(Steady)
(Steady)
(Steady)
(Steady)
(Steady)

## Additonal Items (hidden)
December 7th Release
New dropdown taxonomy markup/CSS | Mandeep/Vijay
Seller registration number | Rajesh
- Keyboard Focus Indication All links have no focus indication because of "outline: 0 none;" Suggestion is to use same effect for hover as for focus (active) | Mandeep
Disable Inventory tab in BCC for QA and Production environments
Secure Cookie

## Desktop Defects
April 28 Release
Defect # | Priority | Summary | Resolution Status | Regression Areas | QA Status | Comments
BBBSL-5149 | Severity/Priority 1 | When you click on LTL truck delivery option it won't allow you to add to cart | Resolved | PDP and quick view for multi PDPM attribute LTL items | Not Tested
PS-31936 | Severity/Priority 1 | Website Issue - Placing Registry Orders | Resolved | Shipping address functionality for registry item checkout. | Not Tested
PS-32010 | Severity/Priority 1 | Endeca Phrases are not firing in Production | Resolved | Partial search results | Not Tested
BBBSL-5014 | Severity/Priority 2 | Don't allow web-only SKUs to add more items to cart than are available | Resolved | Adding VDC and non VDC items from different sections and validating inventory from PDP, Registry pages, cart page, wish list page, SFL section and validating inventory during checkout.
BBBSL-5340 | Severity/Priority 2 | When adding an item cart from registry, perform full quanity check instead of just > 0 check. | Resolved | Adding registry items (VDC & Non-VDC) to cart from PDP with registry context and from registry. | Not Tested
BBBSL-5405 | Severity/Priority 2 | Addition of Int'l Billing Countries | Resolved | Billing address on billing payment page, Payment flow during checkout, Order.xml for a particular order. | Not Tested
BBBSL-5155 | Severity/Priority 3 | "Free delivery" message for LTL products, is shown twice | Resolved | PDP and quick view for multi PDPM attribute LTL items | Not Tested

## Mobile Defects
April 28 Release
Defect # | Priority | Title | Resolution Status | Regression Areas | QA Status | Comments
BSL-3396 | Severity/Priority 2 | Coupon Applied and Discount taken Confirmation | Resolved | Below Pages on Mobile site for all sites Cart page, Payment Page Preview Page | Not Tested
BSL-3302 | Severity/Priority 2 | Mobile App - P2DA Howbook: PDP displaying names of the colors | Resolved | All PDP page - Collection, MSWP, accessory Page | Not Tested

## Known Issues
April 28 Release
JIRA Defect ID | Priority | Issue Description | Impacted Area | Comments