## Index
Summary
Date | 2015-06-07
Track | Application Support
Created by | Neeraj Uttreja
Release Date | 2015-06-07
Release Number | 2.08.01.001
Location of EAR | /local1/atg/weblogic/application/bbb_prod/BBBStore.ear /local1/atg/weblogic/application/bbb_pub/BBBStore.ear /local1/atg/weblogic/application/bbb_stg/BBBStore.ear
Reviewed by | Rishabh Garg
Scope | JIRA Defects [Desktop Baby, Desktop BBB, Desktop Canada, Mobile Baby, Mobile BBB and Mobile Canada]
Prerequisite | June PS must be deployed
(Steady)
(Steady)
(Steady)
(Steady)
(Steady)
(Steady)
(Steady)
(Steady)
(Steady)
(Steady)
(Steady)
(Steady)

## Additonal Items (hidden)
December 7th Release
New dropdown taxonomy markup/CSS | Mandeep/Vijay
Seller registration number | Rajesh
- Keyboard Focus Indication All links have no focus indication because of "outline: 0 none;" Suggestion is to use same effect for hover as for focus (active) | Mandeep
Disable Inventory tab in BCC for QA and Production environments
Secure Cookie

## Desktop Defects
July 06 Release
BBB/ Sapient | Defect # | Priority | Summary | Resolution Status | Regression Areas | QA Status | Comments
Sapient | BBBSL-3291 | Severity/Priority 2 | Certona - implement code to capture quick views | Resolved | Certona calls on quick view from all places | Not Tested
Sapient | BBBSL-4354 | Severity/Priority 2 | Paginated pages - add canonical element on the inner pages of paginated series | Resolved | 1)Canonical URL of Brand, Search & PLP pages. 2)Next & Prev URLs of Brand, Search & PLP pages. | Not Tested
Sapient | BBBSL-5151 | Severity/Priority 2 | College Pack and Hold Changes | Resolved | College Scenarios. Pack and hold option on Shipping page. | Not Tested
Sapient | BBBSL-5166 | Severity/Priority 2 | 3rd party pixels to be fired for international orders | Resolved | 1. International Order submit process and PO file processing for BBB US and Baby Desktop and mobile both. 2. Omniture Tag firing on International Order submit. | Not Tested
Sapient | BBBSL-5189 | Severity/Priority 2 | Unable to Add to cart or Registry from Quick View | Resolved | Add to cart from PDP/Quick View for MSWP, Collection and Accessory items. | Not Tested
Sapient | BBBSL-5198 | Severity/Priority 2 | Shorten L1 Heros and Expand L1 Categories | Resolved | L1 Categories pages. | Not Tested
Sapient | BBBSL-5199 | Severity/Priority 1 | Data feeds for Commission Junction for Bedbath, Bedbath Canada and Baby do not include all products on the sites | Resolved | Commission Junction Marketing Feed for all the three sites | Not Tested
Sapient | BBBSL-5312 | Severity/Priority 2 | Content within "P_Description" as shown in JSP Ref | Resolved | Endeca property for p_description, to be verfied from EndecaClient | Not Tested
Sapient | BBBSL-5852 | Severity/Priority 2 | Fw: Customer service - URGENT - Customer feedback not being routed to customer service | Resolved | Valid Contact Emails recieved | Not Tested
Sapient | BBBSL-5887 | Severity/Priority 2 | SKU available on web, but blocked/flagged/below the line in PIM | Resolved | Regression area is the registry view page for both guest and owner view where flagged off item was showing add to cart. | Not Tested
Sapient | BBBSL-5941 | Severity/Priority 2 | Customer coupon redemption issue | Resolved | Checkout Flow when we add coupons. While calling Coupon webservice i.e. from billing page. | Not Tested
Sapient | BBBSL-5987 | Severity/Priority 3 | Clearance L1 Redirect to Listing Style Page | Resolved | Clearance Page/PLP , Pagination on category pages | Not Tested
Sapient | BBBSL-5988 | Severity/Priority 2 | Post Chameleon Borderfree Unconfirmed Orders | Resolved | International PO file processing | Not Tested
Sapient | BBBSL-5915 | Severity/Priority 3 | Automate BCC deployments | Resolved | PIM Feed Deployment | Not Tested
Sapient | BBBSL-5991 | Severity/Priority 2 | Create an Account Option Added to Top Left of Order Confirmation Page | Resolved | Order Confirmation Page for Gust checkout page | Not Tested
BBB | BBBSL-5984 | Severity/Priority 3 | Mobile Omniture - Registry gift giver not firing correctly | Resolved | Registry gifter view page, Omniture call value eVar15 only. | NA
BBB | AC-69 | Severity/Priority 2 | Cart/Checkout Errors are not read to the User | Resolved | BBBY and BABY sites,In Shipping,Billing,Payment pages.Focus is returned to top of the invalid input and also it reads The error message. And in coupon page it reads the invalid alert message | NA

## Mobile Defects
June 08 Release
July 06 Release
BBB/ Sapient | Defect # | Priority | Title | Resolution Status | Regression Areas | QA Status | Comments
Sapient | BSL-3414 | Severity/Priority 3 | Mobile:: PLP URL does not remove endeca dimensions, facets & parameters on removing filters | Resolved | PLP and search url refresh only. | Not Tested
Sapient | BSL-3513 | Severity/Priority 3 | Omniture/Certona. Certona null search tag fires on all search terms | Resolved | Certona call on search page | Not Tested
Sapient | BSL-3546 | Severity/Priority 3 | Mobile - Add college checklist PDFs to mobile | Resolved | PDF functionality on desktop, should work as expected. existing find my college functionality on mobile, should work as expected. | Not Tested
Sapient | BSL-2805 | Severity/Priority 3 | Google+ Icons | Resolved | On all pages where we see social icons on footer, functional area could be browse and search | Pass
BBB | BSL-3205 | Severity/Priority 3 | Form behavior doesn't allow user to switch focus to next field by clicking the return key | Resolved | NA | Not Tested
Sapient | BSL-3592 | Severity/Priority 3 | Add Facebook Pixels to Mobile | Resolved | Across all the functional flows of the websites | Not Tested
BBB | BSL-3400 | Severity/Priority 3 | Mobile Omniture - Registry gift giver not firing correctly | Resolved | Registry gifter view page, Omniture call value eVar15 only. | NA
BBB | BSL-3680_ | Severity/Priority 2 | Mobile - YourAmigo Tracking Code fix - Updated fix needed for Baby mobile | Resolved | Go to BuyBuyBaby Mobile site.select view source.The correct Tracking code is 52657396 which is the same as set up for the buybuybaby desktop conversion confirmation page .It takes BuyBuyBaby track idenifier | NA

## Known Issues
July 06 Release
JIRA Defect ID | Priority | Issue Description | Impacted Area | Comments