## Index
Summary
Date | 2015-11-05
Track | Application Support
Created by | Neeraj Uttreja
Release Date | 2015-11-05
Release Number | 2.08.01.001
Location of EAR | /local1/atg/weblogic/application/bbb_prod/BBBStore.ear /local1/atg/weblogic/application/bbb_pub/BBBStore.ear /local1/atg/weblogic/application/bbb_stg/BBBStore.ear
Reviewed by | Ajay Sharma
Scope | JIRA Defects [Desktop Baby, Desktop BBB, Desktop Canada, Mobile Baby, Mobile BBB and Mobile Canada]
Prerequisite | June PS must be deployed
(Steady)
(Steady)
(Steady)
(Steady)
(Steady)
(Steady)
(Steady)
(Steady)
(Steady)
(Steady)
(Steady)
(Steady)

## Additonal Items (hidden)
December 7th Release
New dropdown taxonomy markup/CSS | Mandeep/Vijay
Seller registration number | Rajesh
- Keyboard Focus Indication All links have no focus indication because of "outline: 0 none;" Suggestion is to use same effect for hover as for focus (active) | Mandeep
Disable Inventory tab in BCC for QA and Production environments
Secure Cookie

## Desktop Defects
May 11 Release
Defect # | Priority | Summary | Resolution Status | Regression Areas | QA Status | Comments
BBBSL-5557 | Severity/Priority 2 | Issue with alt images loading on PDP | Resolved | PDP Image section with alt images | Not Tested
BBBSL-5541 | Severity/Priority 2 | Drop down menus look strange | Resolved | Collection/Accessories page and quick view | Not Tested
BBBSL-5491 | Severity/Priority 2 | Linethrough is applied on price values within the Trending now section | Resolved | Trending now section on Homepage. | Not Tested
BBBSL-5463 | Severity/Priority 2 | For Brands list in type-ahead search, order is not defined (waterford) | Resolved | Type ahead search suggestions. | Not Tested
BBBSL-5435 | Severity/Priority 2 | 'Other Results' matching search for 'catalog' with no actual results. | Resolved | Search Pages Partial Search | Not Tested
BBBSL-3966 | Severity/Priority 2 | Breadcrumbs from Brand Pages Do Not Exist | Resolved | breadcrumbs at PDP omniture variables at PDP | Not Tested

## Mobile Defects
May 11 Release
Defect # | Priority | Title | Resolution Status | Regression Areas | QA Status | Comments
BSL-3344 | Severity/Priority 2 | Only was Price displayed in mob not the current price in Kick Starter page for Registry | Resolved | Top consultant page | Not Tested
BSL-2860 | Severity/Priority 2 | User can't create a registry after removing the optional co-Registrant. | Resolved | Create registry page on mobileweb | Not Tested

## Known Issues
May 11 Release
JIRA Defect ID | Priority | Issue Description | Impacted Area | Comments