## Index
Summary
Date | 2015-12-14
Track | Application Support
Created by | Pramod Kumar Agrawal
Release Date | 2015-12-14
Release Number | 2.08.01.001
Location of EAR | /local1/atg/weblogic/application/bbb_prod/BBBStore.ear /local1/atg/weblogic/application/bbb_pub/BBBStore.ear /local1/atg/weblogic/application/bbb_stg/BBBStore.ear
Reviewed by | Prashant Bhardwaj
Scope | JIRA Defects [Desktop Baby, Desktop BBB, Desktop Canada, Mobile Baby, Mobile BBB and Mobile Canada]
Prerequisite | Oct PS must be deployed
(Steady)
(Steady)
(Steady)
(Steady)
(Steady)
(Steady)
(Steady)
(Steady)
(Steady)
(Steady)
(Steady)
(Steady)

## Additonal Items (hidden)
December 7th Release
New dropdown taxonomy markup/CSS | Mandeep/Vijay
Seller registration number | Rajesh
- Keyboard Focus Indication All links have no focus indication because of "outline: 0 none;" Suggestion is to use same effect for hover as for focus (active) | Mandeep
Disable Inventory tab in BCC for QA and Production environments
Secure Cookie

## Desktop Defects
December 14 Release
BBB/ Sapient | Defect # | Priority | Summary | Resolution Status | Regression Areas | QA Status | Comments
Gemini_JanPS | BBBSL-4508 | Severity/Priority 3 | While creating the Baby registry Clicking upon the event date on calender date is displaying Plain (white) | Resolved |  | Not Tested | Regression area missing
Gemini_JanPS | BBBSL-3744 | Severity/Priority 2 | Cart Analyzer issue - causing the PIM feeds to fail due to asset lock issue | Resolved | Cart Analyzer Feed Deployment PIM feed deployment | Not Tested
Gemini_JanPS | AC-233 | Severity/Priority 3 | Skip to Navigation/Skip to Content | Resolved |  | Not Tested | Regression area missing
Draco_JanPS | BBBSL-7466 | Severity/Priority 2 | IE 8 and IE 10 Conversion Rate | Resolved |  | Not Tested | Regression area missing
Draco_JanPS | BBBSL-7419 | Severity/Priority 2 | Omniture/Certona: Personalized (CR) product "Add to Registry" Event23, evar54 is not firing as expected | Resolved |  | Not Tested | Regression area missing

## Mobile Defects
June 08 Release |  | December 14 Release
BBB/ Sapient | Defect # | Priority | Title | Resolution Status | Regression Areas | QA Status | Comments
Gemini_JanPS | BSL-3897 | Severity/Priority 3 | Omniture/Mobile - ecircular landing page does not have correct content effectiveness | Resolved |  | Not Tested | Regression area missing
Gemini_JanPS | BSL-2096 | Severity/Priority 3 | SEO elements to be added on mobile static pages | Resolved |  | Not Tested | Regression area missing

## Known Issues
December 14 Release
JIRA Defect ID | Priority | Issue Description | Impacted Area | Comments
- Write a review link is not working on Order Summary page. - TBS - On Click on L3 from Menu > L1> L2 > L3 – giving 500 internal server error + Label labels distorted on footer - Mobile (BBB Code issue) - Product QA & A tab on PDP displays message “please try again” search “Sesame potty” and go to PDP of any product - Mobile - Rating and Reviews accordion is not opening - Mobile - Reviews are not coming on PDP – search “Sesame potty” and go to PDP - Mobile - Added item from pending tab to the registry does not displayed in My items tab until user refreshes the My item page - Desktop