## Index
Summary
Date | 2015-12-14
Track | Application Support
Created by | Pramod Kumar Agrawal
Release Date | 2015-12-14
Release Number | 2.08.02.001
Location of EAR | /local1/atg/weblogic/application/bbb_prod/BBBStore.ear /local1/atg/weblogic/application/bbb_pub/BBBStore.ear /local1/atg/weblogic/application/bbb_stg/BBBStore.ear
Reviewed by | Prashant Bhardwaj
Scope | JIRA Defects [Desktop Baby, Desktop BBB, Desktop Canada, Mobile Baby, Mobile BBB and Mobile Canada]
Prerequisite | Oct PS must be deployed
(Steady)
(Steady)
(Steady)
(Steady)
(Steady)
(Steady)
(Steady)
(Steady)
(Steady)
(Steady)
(Steady)
(Steady)

## Additonal Items (hidden)
December 7th Release
New dropdown taxonomy markup/CSS | Mandeep/Vijay
Seller registration number | Rajesh
- Keyboard Focus Indication All links have no focus indication because of "outline: 0 none;" Suggestion is to use same effect for hover as for focus (active) | Mandeep
Disable Inventory tab in BCC for QA and Production environments
Secure Cookie

## Desktop Defects
December 14 Release
BBB/ Sapient | Defect # | Priority | Summary | Resolution Status | Regression Areas | QA Status | Comments
Sapient-AppSupport | BBBSL-7589 | Severity/Priority 1 | Promo attributes in PDPM location do not seem to work when clicked | Resolved | PDPM attributes on PDPs | Pass

## Mobile Defects
June 08 Release |  | December 14 Release
BBB/ Sapient | Defect # | Priority | Title | Resolution Status | Regression Areas | QA Status | Comments

## Known Issues
December 14 Release
JIRA Defect ID | Priority | Issue Description | Impacted Area | Comments
- Write a review link is not working on Order Summary page. - TBS - On Click on L3 from Menu > L1> L2 > L3 – giving 500 internal server error + Label labels distorted on footer - Mobile (BBB Code issue) - Product QA & A tab on PDP displays message “please try again” search “Sesame potty” and go to PDP of any product - Mobile - Rating and Reviews accordion is not opening - Mobile - Reviews are not coming on PDP – search “Sesame potty” and go to PDP - Mobile - Added item from pending tab to the registry does not displayed in My items tab until user refreshes the My item page - Desktop