## Index
Summary
Date | 16/11/2015
Track | Application Support
Created by | Neeraj Uttreja
Release Date | 16/11/2015
Release Number | 2.08.02.001
Location of EAR | /local1/atg/weblogic/application/bbb_prod/BBBStore.ear /local1/atg/weblogic/application/bbb_pub/BBBStore.ear /local1/atg/weblogic/application/bbb_stg/BBBStore.ear
Reviewed by | Shubham Jain
Scope | JIRA Defects [Desktop Baby, Desktop BBB, Desktop Canada, Mobile Baby, Mobile BBB and Mobile Canada]
Prerequisite | Oct PS must be deployed
(Steady)
(Steady)
(Steady)
(Steady)
(Steady)
(Steady)
(Steady)
(Steady)
(Steady)
(Steady)
(Steady)
(Steady)

## Additonal Items (hidden)
December 7th Release
New dropdown taxonomy markup/CSS | Mandeep/Vijay
Seller registration number | Rajesh
- Keyboard Focus Indication All links have no focus indication because of "outline: 0 none;" Suggestion is to use same effect for hover as for focus (active) | Mandeep
Disable Inventory tab in BCC for QA and Production environments
Secure Cookie

## Known Issues
November 16 Release
JIRA Defect ID | Priority | Issue Description | Impacted Area | Comments
| P1 | TBS ¦ Search is not working, no search result page is displaying.
| P1 | TBS ¦ L1/L2/L3 categories are not opening
| P1 | TBS ¦ After changing password when I login again it shows, error message "Oops! There was an error, please try again or call for assistance"
| P1 | After product has been added to Registry from Recommendation tab , the added product does not show up in registry tab.
| P1 | Recommendation tab on Registry view page does not open