## Index
Summary
Date | 2015-11-23
Track | Application Support
Created by | Pramod Kumar Agrawal
Release Date | 2015-11-23
Release Number | 2.08.02.001
Location of EAR | /local1/atg/weblogic/application/bbb_prod/BBBStore.ear /local1/atg/weblogic/application/bbb_pub/BBBStore.ear /local1/atg/weblogic/application/bbb_stg/BBBStore.ear
Reviewed by | Prashant Bhardwaj
Scope | JIRA Defects [Desktop Baby, Desktop BBB, Desktop Canada, Mobile Baby, Mobile BBB and Mobile Canada]
Prerequisite | Oct PS must be deployed
(Steady)
(Steady)
(Steady)
(Steady)
(Steady)
(Steady)
(Steady)
(Steady)
(Steady)
(Steady)
(Steady)
(Steady)

## Additonal Items (hidden)
December 7th Release
New dropdown taxonomy markup/CSS | Mandeep/Vijay
Seller registration number | Rajesh
- Keyboard Focus Indication All links have no focus indication because of "outline: 0 none;" Suggestion is to use same effect for hover as for focus (active) | Mandeep
Disable Inventory tab in BCC for QA and Production environments
Secure Cookie

## Desktop Defects
November 09 Release
BBB/ Sapient | Defect # | Priority | Summary | Resolution Status | Regression Areas | QA Status | Comments
Sapient-AppSupport | BBBSL-6791 | Severity/Priority 2 | Add Custom Offer at End of Description Tags - Like Free Shipping | Resolved | Product Pages ,Brand Pages and Category Landing Pages. | Pass
Sapient-AppSupport | BBBSL-6916 | Severity/Priority 2 | System displaying wrong error message | Resolved | Multi-SKU - Quick view - Error Messaging on add to registry button | Pass
Sapient-AppSupport | BBBSL-7122 | Severity/Priority 2 | Regarding Partial Endeca Baseline Products_Category.txt | Resolved | Search page | Pass
Sapient-AppSupport | BBBSL-7381 | Severity/Priority 2 | Omniture/Certona: revised scode to address defects dated 10/13/15 | Resolved | Desktop Omniture/ Certona call | Pass
Sapeint-Draco | DRACO-879 | Severity/Priority 2 | Omniture/Certona: event30 | Resolved | NA | Pass
Sapeint-Draco | DRACO-805 | Severity/Priority 2 | Returns Modal needs more content? | Resolved | NA | Pass
Sapeint-Draco | DRACO-784 | Severity/Priority 2 | eVar54 (personalization type) and event 82 is not firing when product is being added to cart from Save for Later | Resolved | NA | Pass
Sapeint-Draco | DRACO-783 | Severity/Priority 2 | eVar54 (personalization type) is firing as Null | Resolved | NA | Pass
Sapeint-Draco | DRACO-735 | Severity/Priority 2 | Omniture/Certona: event 82 does not fire for product with accessories on mobile when added to cart | Resolved | NA | Pass

## Mobile Defects
June 08 Release |  | November 09 Release
BBB/ Sapient | Defect # | Priority | Title | Resolution Status | Regression Areas | QA Status | Comments
Sapient | BSL-3779 | Severity/Priority 2 | RKG Micro Conversion Pixel Placement on BBB Mobile ATG E-mail Sign-up page | Resolved | RKG Pixels on MyAccount Page and Email Opt in Functionality. | Pass
Sapient | BSL-4250 | Severity/Priority 2 | /m/getUSTerritoriesFromFlag generating 500 errors in some mobile sessions | Resolved | Cart/Checkout, calls made for getUSTerritoriesFromFlag on checkout/Express Checkout. | Pass
Sapient | BSL-4285 | Severity/Priority 2 | Persistent Login after Creating an Account | Resolved | Across the site for Mobile App | Pass
Sapient-AppSupport | BSL-3718 | Severity/Priority 2 | Prop 21 Value should be more specific based on input search | Resolved | Omniture call on find in store and pick up in store page | Pass
Sapient-AppSupport | BSL-4301 | Severity/Priority 1 | BBBY & Baby Mobile Reg View Page: Add to Cart Missing | Resolved | registry owner pages | Pass

## Known Issues
November 09 Release
JIRA Defect ID | Priority | Issue Description | Impacted Area | Comments
1. TBS- Registration ¦ After doing Registration, user is not redirecting towards my account page, it is showing blank 2. TBS- Search ¦ On searching keywords, blank page displaying to the user 3. TBS- Category ¦ L1 category not opening, showing blank page 4. FF1 - Menu Bar ¦ On click of any menu, page distortion showing 5. Registry services not working on ecomqa endpoint 6. Desktop CA - Banner on Home page is not displaying in full helgth for L1 category