## Index
Summary
Date | 2016-01-27
Track | Application Support
Created by | Pramod Kumar Agrawal
Release Date | 2016-01-27
Release Number | 1/27/16 Build
Location of EAR | /local1/atg/weblogic/application/bbb_prod/BBBStore.ear /local1/atg/weblogic/application/bbb_pub/BBBStore.ear /local1/atg/weblogic/application/bbb_stg/BBBStore.ear
Reviewed by | Shubham
Scope | JIRA Defects [Desktop Baby, Desktop BBB, Desktop Canada, Mobile Baby, Mobile BBB and Mobile Canada]
Prerequisite | Oct PS must be deployed
(Steady)
(Steady)
(Steady)
(Steady)
(Steady)
(Steady)
(Steady)
(Steady)
(Steady)
(Steady)
(Steady)
(Steady)

## Additonal Items (hidden)
December 7th Release
New dropdown taxonomy markup/CSS | Mandeep/Vijay
Seller registration number | Rajesh
- Keyboard Focus Indication All links have no focus indication because of "outline: 0 none;" Suggestion is to use same effect for hover as for focus (active) | Mandeep
Disable Inventory tab in BCC for QA and Production environments
Secure Cookie

## Desktop Defects
January 27 Release
BBB/ Sapient | Defect # | Priority | Summary | Resolution Status | Regression Areas | QA Status | Comments
Sapient-AppSupport | BBBSL-7951 | Severity/Priority 2 | Omniture/Certona: Certona tagging on OOS missing plk tags | Resolved | Certona call for collection, single sku, multi sku & accessories on PDP | Pass
Sapient-AppSupport | BBBSL-7975 | Severity/Priority 2 | Omniture/Certona: order confirmation fires event70 | Resolved | Omniture Events on order confirmation on both TBS and Desktop | Pass
Sapient-AppSupport | PS-42190 | Severity/Priority 2 | OpinionLab feedback tab is flashing | Resolved

## Mobile Defects
June 08 Release |  | January 27 Release
BBB/ Sapient | Defect # | Priority | Title | Resolution Status | Regression Areas | QA Status | Comments

## Known Issues
January 27 Release
JIRA Defect ID | Priority | Issue Description | Impacted Area | Comments
| P1 | -Paypal checkout is not working. It shows: Paypal service is unavailable at this moment. Please try after some time (Mobile - All) | Checkout | Paypal service not working
| P1 | - Error Message "We're sorry, PayPal is currently unavailable. Please select another form of Payment" displays on placing order with paypal Steps: I choose to select Paypal option and Continue on Payment Page on "MultiShipping" with LTL item (Desktop - All) | Checkout | Paypal service not working
| P1 | -Getting Error message "We are sorry! A system error ...." while checkout from cart (Desktop - CA) Login to site Add item 18276879 or any item Click on checkout on Cart page | Checkout
| P1 | -While clicking on apply changes on SPC for shipping address with collection item 212371 - displaying error message - We are sorry ..." (Desktop - Baby) Steps Login on Baby site Search collection item 212371 Add Copco Coffee Cab Small Appliance Slider into cart Click on Checkout on cart On SPC page enter phone details and click on apply changes | Checkout
| P1 | -Internal server error on clicking "checkout with paypal" on cart having regular item with 3 quantity (Desktop - Baby) | Checkout | Paypal service not working