## Index
Summary
Date | 28/8/2015
Track | Application Support
Created by | Shailender Singh
Release Date | 28/8/2015
Release Number | 2.08.02.001
Location of EAR | /local1/atg/weblogic/application/bbb_prod/BBBStore.ear /local1/atg/weblogic/application/bbb_pub/BBBStore.ear /local1/atg/weblogic/application/bbb_stg/BBBStore.ear
Reviewed by | Prashant Bhardwaj
Scope | JIRA Defects [Desktop Baby, Desktop BBB, Desktop Canada, Mobile Baby, Mobile BBB and Mobile Canada]
Prerequisite | Oct PS must be deployed
(Steady)
(Steady)
(Steady)
(Steady)
(Steady)
(Steady)
(Steady)
(Steady)
(Steady)
(Steady)
(Steady)
(Steady)

## Additonal Items (hidden)
December 7th Release
New dropdown taxonomy markup/CSS | Mandeep/Vijay
Seller registration number | Rajesh
- Keyboard Focus Indication All links have no focus indication because of "outline: 0 none;" Suggestion is to use same effect for hover as for focus (active) | Mandeep
Disable Inventory tab in BCC for QA and Production environments
Secure Cookie

## Desktop Defects
August 28 Release
BBB/ Sapient | Defect # | Priority | Summary | Resolution Status | Regression Areas | QA Status | Comments
Sapient | BBBSL-6090 | Severity/Priority 2 | Add SalesDataFeedScheduler to AN SLM-02 JVM | Resolved | No Regression | PASS
Sapient | BBBSL-6006 | Severity/Priority 2 | Omniture/Certona: out of stock recommendations serving the right products? | Resolved | OOS Functionality in Dektop and Mobile | PASS
Sapient | BBBSL-4173 | Severity/Priority 2 | Update copyright coding | Resolved | Copyright texts in application, PDP, PLP
Sapient | BBBSL-4731 | Severity/Priority 2 | UX: The "Search Tips" link wrapping up in next row on Kickstarters -> Registry landing page. | Resolved | Registry landing page
Sapient | BBBSL-6076 | Severity/Priority 2 | Multiple ATG accounts for same email | Resolved | DSK - Update email in Personal Info
Sapient | BBBSL-6086 | Severity/Priority 2 | Paginated pages - correct rel next and prev | Resolved | PLP
Sapient | BBBSL-6237 | Severity/Priority 2 | DSK/Omniture/Certona. Omniture, select your country pop up fires evars1-8 | Resolved | Omniture events
Sapient | BBBSL-3753 | Severity/Priority 2 | LTL:"Move To Cart" Button is enabled for out of stock LTL saved item in cart | Resolved | Cart Page
Sapient | BBBSL-3794 | Severity/Priority 3 | Registry Checklist ¦check-box to select the items for the checklist is not working ,User unable to select or check the check-box | Resolved | Registry Check List Page
Sapient | BBBSL-3817 | Severity/Priority 3 | Send me a copy opt in box in ATG emails | Resolved | Email Cart/PDP/Single Reg, Multiple Registry/Email baby,bridal book
Sapient | BBBSL-5158 | Severity/Priority 3 | Error message for Expired credit card | Completed | Checkout
Sapient | BBBSL-3818 | Severity/Priority 3 | evar46 is not getting fired as expected on adding item to registry before logging in | Completed | PDP
Sapient | BBBSL-6027 | Severity/Priority 2 | Omniture/Certona: need to tag all the error pages. | Completed | Error Pages in all application, Cart/Checkout
Sapient | BBBSL-5818 | Severity/Priority 2 | College products - Eligible for Shop Now, able to select previous months dates. | Completed | Checkout /Shop Now, Ship Later (Pack & Hold) functionality for college products
Sapient | PS-28012 | Severity/Priority 2 | Default address for PayPal checkout after returning form preview page and making changes to cart page | Already Fixed | Paypal checkout
Sapient | PS-35040 | Severity/Priority 2 | Omniture/Certona: Omniture tagging for "also check out" container on college is wrong | Completed | Omniture events, PDP/PLP
Sapient | BBBSL-3756 | Severity/Priority 3 | Find Your College -Wrong text on No Stores Found modal | Resolved | Find a store page
Sapient | BBBSL-5421 | Severity/Priority 3 | Please change browser/page title for search result pages | Resolved | All kind of search pages and all tabs,SWS on Desktop
Sapient | BBBSL-4976 | Severity/Priority 2 | Omniture/Certona. Products bought in the order confirmation email do not have mcid | Resolved | Order confirmation email.
Sapient | BBBSL-5355 | Severity/Priority 3 | Parameter in Search URL after changing List/Grid View (NTPC) | Resolved | Verify SEARCH URL after changing LIST/GRID view -serach a keyword
Sapient | BBBSL-5193 | Severity/Priority 2 | Omniture/Certona: Need proper tagging on the personal page | Resolved | Personal Store Page ,PDP pages,Quick Vie page
Sapient | BBBSL-2302 | Severity/Priority 2 | Bazarvoice feed issue | Resolved | Feed Generation
Sapient | BBBSL-4898 | Severity/Priority 2 | Registry Names Clickable | Resolved | Registry search page
Sapient | BBBSL-4913 | Severity/Priority 3 | Unsubscribe from product inventory status | Resolved | Unsubscribe functionality
Sapient | BBBBSL-4627 | Severity/Priority 3 | Quick View Omniture | Resolved | Quick View from registry pages
Sapient | BBBSL-3823 | Severity/Priority 2 | Registry Kickstarters - Add canonical element | Resolved | Kckstarter , top-consultant,shop this look pages
Sapient | BBBSL-3944 | Severity/Priority 3 | last viewed items - when I am on a pdp, the item I am looking at is in last viewed items | Resolved | PDP
Sapient | BBBSL-4501 | Severity/Priority 2 | Omniture - email sign up is not set up correctly | Resolved | - Creation of account from order confirmation page on sister site with same account.
Sapient | BBBSL-5114 | Severity/Priority 2 | Find In Store is enabled for vendor direct shipping collection items | Resolved | Desktop Collection PDP
Sapient | BBBSL-5555 | Severity/Priority 2 | BFE: Show Me and Sort by down arrows are missing on My Items tab. | Resolved | Desktop Registry owner view
Sapient | BBBSL-4335 | Severity/Priority 3 | Redirect "not available" product page to a similar product page instead of ever living PDP | Already Fixed | Everliving PDP,PDP
Sapient | BBBSL-4819 | Severity/Priority 3 | Shipping Charges not displaying in Email Account. | CNR | No regression as CNR
Sapient | BBBSL-4355 | Severity/Priority 3 | Paginated pages - invalid URLs should return 404 error | Already Fixed | No regression as already fixed
Sapient | BBBSL-5507 | Severity/Priority 3 | Total Savings - Shows zero cost | Already Fixed | NA
Sapient | BBBSL-4704 | Severity/Priority 3 | Channel, prop2 and prop3 are not getting fired as expected on clicking quick view on Collection PDP page | Already Fixed | No regression as already fixed
Sapient | BBBSL-4508 | Severity/Priority 3 | While creating the Baby registry Clicking upon the event date on calender date is displaying Plain (white) | CNR | NA
Sapient | BBBSL-4520 | Severity/Priority 2 | Estimated Shipping information is missing in email account. | CNR | No regression as CNR
Sapient | BBBSL-5427 | Severity/Priority 2 | Brand name appears twice in the browser titles of "Shop by Brand" pages | Already Fixed | Brand Name as browser titles of "Shop by Brand" pages
Sapient | BBBSL-5755 | Severity/Priority 2 | Canadian site allowing shipment to PO Box -Order CAN3030100061 | CNR | NA
Sapient | BBBSL-5890 | Severity/Priority 1 | Google Merchant Inventory Feed issues (RKG SEM PLAs) - Updated Pricing Issues | Already Fixed | No regression as already fixed
Sapient | BBBSL-4763 | Severity/Priority 2 | Omniture - CLP do not have correct tagging | Already Fixed | NA
Sapient | BBBSL-4288 | Severity/Priority 3 | Pagination not working on " Guides & Advice " page | Resolved | Guides and Advice Registry Pages
Sapient | BBBSL-3742 | Severity/Priority 3 | Update Omniture data feeds to generate a zero byte file when no data is available. | Resolved | omniture feed files on all sites
Sapient | BBBSL-4626 | Severity/Priority 3 | Prop 2 is firing incorrectly for Compare Products. | Resolved | omniture events on PLP and product comparison pages
Sapient | BBBSL-4351 | Severity/Priority 2 | Updating the Social Feed on the Registry Web Page | Resolved | Baby registry landing page
Sapient | BBBSL-6027 | Severity/Priority 2 | Omniture/Certona: need to tag all the error pages. | Resolved | No regression as no code commit
Sapient | BBBSL-4523 | Severity/Priority 2 | COLOR & SIZE details are missing in Email Account of In-Store Pickup Orders. | Resolved | Store pickup email
Sapient | BBBSL-2932 | Severity/Priority 2 | BCC Control of Website Headers and Footers | Resolved | Footer part on all desktop sites
Sapient | BBBSL-5948 | Severity/Priority 2 | Edgecase code is on buybuyBaby | Resolved | No regression area
Sapient | PS-34405 | Severity/Priority 3 | Promotional attribute deletions | Resolved | product attributes on PDP

## Mobile Defects
June 08 Release |  | August 28 Release
BBB/ Sapient | Defect # | Priority | Title | Resolution Status | Regression Areas | QA Status | Comments
Sapient | BSL-3846 | Severity/Priority 2 | Add MediaMath Pixels to BBB and Baby Mobile Sites | Resolved | Across all the functional flows of the 3 mobile sites - US, Baby, Canada | PASS
Sapient | BSL-2752 | Severity/Priority 3 | Make Mobile HP Banner an Text Area | Resolved | Mobile homepage banner, below homepage corousel
Sapient | BSL-3202 | Severity/Priority 3 | Add to Registry not landing on correct page when user in native PDP | Resolved | Add to registry from PDP/SFL
Sapient | BSL-3231 | Severity/Priority 3 | Mobile Site - Find Store using my location is not working | Resolved | Find Store
Sapient | BSL-3483 | Severity/Priority 3 | Omniture/Certona: evar 1 fires on L1 pages with wrong values | Resolved | L1 - Category landing Page
Sapient | BSL-3487 | Severity/Priority 2 | Omniture/Certona: Omniture evar1 when clicking on a product from a collection/accessories page | Resolved | Collection PDP, Accessories PDP
Sapient | BSL-3488 | Severity/Priority 2 | Omniture/Certona: Omniture everliving pdp tagging is incorrect | Resolved | Everliving PDP
Sapient | BSL-3490 | Severity/priority 2 | Fires "clicked carousel item" when clicking on the college carousel AND THEN it fires as an internal campaign id | Resolved | Shop for College Page
Sapient | BSL-3491 | Severity/priority 2 | if pagename is search and v1 isnot search, then this v1 should be internal campaign, if this is not an email campaign. However, the tagging shows v1 = Shop kate spade new york. The right way tagging this page is v1=internal campaign and v3 = homepage_herocarousel2-Shop kate spade new york. Because of this defect, mobile can not report on internal promos status. please see hpspot2 tagging tab | Resolved | Home Page
Sapient | BSL-3734 | Severity/Priority 1 | coupon wallet, apply coupon fires multiple times, once for every step of the checkout process | Resolved | Coupon Wallet
Sapient | BSL-3851 | Severity/Priority 4 | track order page has wrong pagename And it's missing remaining content effectiveness values | Resolved | Track Order Page
Sapient | BSL-3875 | Severity/Priority 3 | Shipping methods fires the same event as shipping | Resolved | Checkout page
Sapient | BSL-3878 | Severity/Priority 4 | Omniture/Mobile - PLP usage (grid/list view) | Resolved | PLP
Sapient | BSL-3879 | Severity/Priority 3 | Omniture/Mobile - email sign up | Resolved | Home Page
Sapient | BSL-3883 | Severity/Priority 3 | Clicking on track order does not fire prop12 | Resolved | Track Order Page
Sapient | BSL-3894 | Severity/Priority 3 | Certona container on home page named inconsistently with desktop | Resolved | Home Page, PDP, Null Search
Sapient | BSL-3895 | Severity/Priority 3 | Omniture/Mobile - Gift Giver Page | Resolved | Gift Giver pages
Sapient | BSL-2096 | Severity/Priority 4 | SEO elements to be added on mobile static pages | Resolved | PDP/PLP/Cart Checkout
Sapient | BSL-3897 | Severity/Priority 3 | ecircular landing page does not have correct content effectiveness | Resolved | Circular Landing Page
Sapient | BSL-3322 | Severity/Priority 3 | Need to add RKG Micrro Conversion Pixels on Mobile ROPUS conversions | Completed | Order Confirmation Page
Sapient | AC-85 | Severity/Priority 2 | star rating for each item conveyed as CSS background image, no alternative in HTML | Completed | PDP/PLP
Sapient | AC-108 | Severity/Priority 3 | Compare Products bottom bar - when present - does not allow removal of individual items with the keyboard or confirm addition | Already Fixed | NA
Sapient | AC-110 | Severity/Priority 3 | Share link opens dropdown menu with social media/email options, but this is only shown when hovering with the mouse | Completed | Registry Owner View
Sapient | AC-113 | Severity/Priority 2 | once a modal is closed, focus is returned to the top of the document | Completed | On all the Modals in the site
Sapient | AC-115 | Severity/Priority 3 | Email, "Create an account", "Email", "Password", "Sign In" have tabindex attributes that make them first focusable controls. After "Sign In", focus cycles to top of document (common header etc). Most notably, "Show password" checkbox and the two "Faceb... | Completed | Login Page
Sapient | AC-118 | Severity/Priority 3 | Account - Saved Items, there are multiple "X Reviews", "Update", "Remove" links with no further context | Completed | PLP, PDP, Quick view, cart , saved items page
Sapient | AC-120 | Severity/Priority 3 | multiple "View collection" links without context | Completed
Sapient | AC-121 | Severity/Priority 3 | various "X Reviews" and "Write a review" links lack context about which product they refer to | Completed | PLP, PDP, Quick view, partial search,cart page
Sapient | AC-126 | Severity/Priority 3 | checking a "Compare" checkbox returns focus to top of the document | CNR | NA
Sapient | AC-127 | Severity/Priority 3 | Selecting the initial state on the "Select Type" <select> element in "Create a Registry" unexpectedly navigates to the Registries Page | Already Fixed | NA
Sapient | AC-134 | Severity/Priority 3 | large number of "Quick view" controls and "Compare" checkboxes lack context (what product they relate to) | Completed | PLP
Sapient | AC-138 | Severity/Priority 3 | tab panel ("Product Information", "Ratings & Reviews", "Product Q&A") lacks appropriate ARIA roles and attributes to identify its structure/functionality | Completed | PDP
Sapient | AC-142 | Severity/Priority 3 | the "remaining characters" counter on the <textarea> is not announced to AT users | Completed | Contact Us Page
Sapient | AC-145 | Severity/Priority 3 | View cart contents control requires additional ARIA attributes (aria-controls, aria-expanded) to indicate its function as a disclosure control and to convey the current status of the content it relates to (whether cart contents are shown or hidden). "V... | Completed | Checkout Page
Sapient | AC-160 | Severity/Priority 3 | type-ahead search suggestions are not announced to AT users | Completed | Search Bar and Search Flyout
Sapient | AC-162 | Severity/Priority 3 | "Fine tabletop & giftware" etc checkboxes need a <fieldset>/<label> to provide grouping and context | Already Fixed | NA
Sapient | AC-233 | Severity/Priority 3 | Skip to Navigation/Skip to Content | Completed | Home Page
Sapient | BSL-3849 | Severity/Priority 3 | Omniture/Mobile - evar46 | Resolved | Registry Landing page
Sapient | AC-154 | Severity/Priority 2 |  | Resolved | Registry no search result page
Sapient | AC-214 | Severity/Priority 2 | A visually impaired customer is not able to submit their comment due to the visual captcha | Resolved | Contact us page.
Sapient | PS-28019 | Severity/Priority 2 | College City name throws Error | Resolved | Find a college page
Sapient | CM-23411/ BBBSL-6491 | Severity/Priority 3 | Gift Card msg correction | Resolved | No Regression area
Sapient | AC-68 | Severity/Priority 2 | Kickstarters shop_this_look | Resolved | No regression area
Sapient | AC-67 | Severity/Priority 2 | Kickstarters details page | Resolved | No regression area
Sapient | PS-25219 | Severity/Priority 2 | Endeca Stop Words removal | Resolved | Seaerch Functionality
Sapient | PS-31544 | Severity/Priority 3 | Endeca related search not in order | Resolved | Breadcrum fubctionality
Sapient | PS-23404 | Severity/Priority 3 | Please remove "store" from the breadcrumb link for home | Resolved | All breadcrumb links
Sapient | PS-33921 | Severity/Priority 2 | Omniture/Certona: evar1 fires when adding to registry from collection quick view | Resolved | - Creation of account from order confirmation page on another site with same account
Sapient | PS-33612 | Severity/Priority 2 | My Offers Design Fixes | Resolved | My offers page
Sapient | AC-61 | Severity/Priority 2 | Accessibility - BBBY Mobile | Resolved | Mobile PLP
Sapient | AC-109 | Severity/Priority 3 | For out of stock items, "Out of stock" is not read for with "Notify me when this item is available." | Resolved | Quickview and PDP desktop
Sapient | BSL-3486 | Severity/Priority 2 | Omniture/certona: Omniture event26 does not fire properly | Resolved | NA
Sapient | BSL-3281 | Severity/Priority 3 | BFE International- Item retains in the cart after placing international order | Resolved | No regression as already fixed
Sapient | PS-27752 | Severity/Priority 3 | CSR Store Page (BOPUS) - View Disabled states not showing Disabled states | Resolved | No regression area
Sapient | BSL-2928 | Severity/Priority 3 | Adding an item from friends registry to shopping cart | Resolved | NA
Sapient | BSL-3848 | Severity/Priority 4 | Omniture/Mobile - evar15 [Minhaj 28 July] Duplicate of BSL-3400 | Resolved | NA
Sapient | AC-56 | Severity/Priority 2 | Mobile - Unable to proceed past Address verification pop up | Resolved | No regression as already fixed
Sapient | AC-45 | Severity/Priority 2 | Not being able to add item to cart/wishlist when Voice over is turned on | Resolved | NA
Sapient | AC-7 | Severity/Priority 2 | Accessibility-LoginPage-The New Customer and Existing Customer areas need to be broken out | Resolved | NA
Sapient | AC-52 | Severity/Priority 2 | Add to Cart :: Unable to proceed after adding item to Cart | Resolved | No regression as already fixed
Sapient | AC-50 | Severity/Priority 2 | Mobile Accessibility :: Login issues | Resolved | No regression as already fixed
Sapient | BSL-3850 | Severity/Priority 4 | Find my college page has no content effectiveness tagging | Resolved | Find my college page
Sapient | PS-32070 | Severity/Priority 3 | Incorrect Error Message for CVC | Resolved | NA
Sapient | BSL-3487 | Severity/Priority 2 | Omniture/Certona: Omniture evar1 when clicking on a product from a collection/accessories page | Resolved | Mobile Collection and Accessory PDP
Sapient | BSL-3109 | Severity/Priority 3 | Store Locator is not sorted A to Z as per the province | Resolved | Store locator page
Sapient | BSL-3484 | Severity/Priority 2 | Popular categories is not a product finding method. Evar1 should not fire | Resolved | Mobile Home Page
Sapient | BSL-3488 | Severity/Priority 2 | event56, Does not fire on ever living pdp. | Resolved | Mobile Everliving PDP
Sapient | BSL-3489 | Severity/Priority 2 | content effectiveness values do not fire for ever living pdp | Resolved | Mobile Everliving PDP
Sapient | PS-32941 | Severity/Priority 2 | International Sites - Full Cart - Certona rec container only 2 items are displayed | Resolved | cart page

## Known Issues
August 28 Release
JIRA Defect ID | Priority | Issue Description | Impacted Area | Comments