## Index
Summary
Date | 2014-01-31
Track | Application Support
Created by | Imran Ali Khan
Release Date | 2014-01-31
Release Number | 2.04.01.01
Location of EAR | /local1/atg/weblogic/application/bbb_prod/BBBStore.ear /local1/atg/weblogic/application/bbb_pub/BBBStore.ear /local1/atg/weblogic/application/bbb_stg/BBBStore.ear
Reviewed by | Sarvex Jatasra
Scope | JIRA Defects [Desktop Baby, Desktop BBB, Desktop Canada, Mobile Baby, Mobile BBB and Mobile Canada] STOFU Full Build
(Steady)
(Steady)
(Steady)
(Steady)
(Steady)
(Steady)
(Steady)
(Steady)
(Steady)
(Steady)
(Steady)
(Steady)

## Desktop Defects
Jan 31 Release
Defect # | Priority | Summary | Resolution Status | Regression Areas | QA Status | Comments
BBBSL-1925 | Severity/Priority 3 | On clicking Update for an item in the cart , displays System error on the Full cart page. | Resolved | BOPUS
BBBSL-1945 | Severity/Priority 3 | BBBSL-1926 Add to cart” button in the Find in Store popup is not displaying in the below scenarios. | Resolved
BBBSL-1946 | Severity/Priority 4 | BBBSL-1926 Add to cart” button in the Find in Store popup is not displaying in the below 2 scenarios. | Resolved
BBBSL-1976 | Severity/Priority 3 | Shipping group should merge if the difference is just due to upper/lower or left/right spaces in first/last/company name. | Resolved
BBBSL-2019 | Severity/Priority 3 | NPE on SearchInStoreDroplet | Resolved
BBBSL-2051 | Severity/Priority 3 | Registry Manage ¦ Too many URL Parameters | Resolved | Registry
BBBSL-2054 | Severity/Priority 4 | Canada is not selected in the country drop down from the billing popup on the payment page for the canada site. | Resolved | Checkout
BBBSL-2101 | Severity/Priority 3 | OOPS page on order placing with express checkout | Resolved | Checkout
BBBSL-2107 | Severity/Priority 3 | For an out of stock accessory product it was not showing out of stock message. | Resolved
BSL-1801 | Severity/Priority 3 | RKG - Dart Floodlight Tags not loading correctly during Test Orders | Resolved | 3rd Party Integrations
BSL-1842 | Severity/Priority 4 | Button Text on Cart Page | Resolved | UI/User experience
BSL-1883 | Severity/Priority 3 | Video Transcript is displayed but no link for Video | Resolved
BSL-1988 | Severity/Priority 4 | bug on Baby site | Resolved
BSL-2053 | Severity/Priority 3 | Gift Message: Not showing number of chars left as I enter gift message | Resolved
BSL-2256 | Severity/Priority 4 | Create Wedding Registry Page Has Incorrect Headline | Resolved
BSL-2259 | Severity/Priority 3 | VDC: Expected delivery date in desktop and mobile web not matching. | Resolved
BSL-2261 | Severity/Priority 4 | Task160- PID not displaying for few pages on mobile sites. | Resolved
PS-16953 | Severity/Priority 3 | Build machine cleanup | Resolved
PS-17047 | Severity/Priority 3 | Shop By Brand page issue | Resolved
PS-17376 | Severity/Priority 4 | SKU # (41292242): Product Inquiry | Resolved
PS-17417 | Severity/Priority 4 | Fw: Registry Account Issue: Website Issue Reported | Resolved
PS-17451 | Severity/Priority 4 | Website Issue Reported | Resolved
PS-17510 | Severity/Priority 3 | Brand Name Showing Incorrectly In Search | Resolved | Data feeds and pushes

## Additonal Items (hidden)
December 7th Release
New dropdown taxonomy markup/CSS | Mandeep/Vijay
Seller registration number | Rajesh
- Keyboard Focus Indication All links have no focus indication because of "outline: 0 none;" Suggestion is to use same effect for hover as for focus (active) | Mandeep
Disable Inventory tab in BCC for QA and Production environments
Secure Cookie

## Mobile Defects
Jan 31 Release
Defect # | Priority | Title | Resolution | Regression Areas | QA Status | Comments
BSL-2015 | Severity/Priority 3 | Baby App: MENU->CONTACT US->In Our Stores->store locations->Pagenot found error: | Resolved
BSL-2037 | Severity/Priority 4 | Baby Mobile Web - Store Map/Directions not working on FIS page | Resolved
BSL-2064 | Severity/Priority 4 | CA Mobile Site - Add New Address modal on Checkout displays postal code field watermark as 'Zip' | Resolved
BSL-2081 | Severity/Priority 3 | background is scrolling when sliding up and down on the menu | Resolved
BSL-2119 | Severity/Priority 4 | BSL-2117 Remove hard coded timeout value for Bazaar voice Product review service call | Resolved
BSL-2134 | Severity/Priority 3 | White line display's on Search screen | Resolved
BSL-2136 | Severity/Priority 3 | Not getting email from Mobile on Gmail account | Resolved
BSL-2196 | Severity/Priority 4 | Shipping method charge format displays as $0 instead of $0.00 | Resolved
BSL-2198 | Severity/Priority 4 | Contact us_via phone : Unable to make a call. | Resolved
BSL-2212 | Severity/Priority 4 | BBB US - Account - Email field shows last name | Resolved
BSL-2324 | Severity/Priority 3 | Mobile ¦ internal server error when user is trying to select a Greeting Card and proceed to checkout. | Resolved
BSL-2325 | Severity/Priority 3 | Mobile ¦ Save for later throwing Internal Server Error | Resolved
WEB-147 | Severity/Priority 3 | In Find a Store the Logo for Stores with CPWM are not displaying | Resolved
WEB-153 | Severity/Priority 3 | Shop By Brand - Click on Letter Not Working | Resolved
WEB-162 | Severity/Priority 4 | Missing data in tag man data layer | Resolved
WEB-164 | Severity/Priority 4 | No space after the colon (:) in Saved Items Section for Color descriptor | Resolved
WEB-165 | Severity/Priority 4 | You save price displays twice on cart and wrong price on preview | Resolved
WEB-185 | Severity/Priority 3 | Invalid color and size item attribute, on multi-shipping 'gift option' page | Resolved
WEB-188 | Severity/Priority 4 | No Spacing on Item Level Messaging for Saved Items | Resolved
WEB-27 | Severity/Priority 3 | Size should be on new line | Resolved

## Known Issues
Jan 31 Release
JIRA Defect ID | Priority | Issue Description | Impacted Area | Comments
BBBSL-2307 | Severity/Priority 3 | Not able to "check out" with multiple Gift Card when there is no amount due | Checkout
BBBSL -2306 | Severity/Priority 3 | Not able to remove applied gift card from payment page | Checkout
BSL-2414 | Severity/Priority 3 | Cart not refreshed on changing bopus item to ship this item on cart page | Mobile Cart Page
BSL-2415 | Severity/Priority 3 | 500 internal server error intemittently on cart refresh | Mobile Cart Page