## Index
Summary
Date | 2014-01-17
Track | Application Support
Created by | Ishu Mehta
Release Date | 2014-01-17
Release Number | 2.03.01.01
Location of EAR | /local1/atg/weblogic/application/bbb_prod/BBBStore.ear /local1/atg/weblogic/application/bbb_pub/BBBStore.ear /local1/atg/weblogic/application/bbb_stg/BBBStore.ear
Reviewed by | Sarvex Jatastra
Scope | JIRA Defects [Desktop Baby, Desktop BBB, Desktop Canada, Mobile Baby, Mobile BBB and Mobile Canada]
(Steady)
(Steady)
(Steady)
(Steady)
(Steady)
(Steady)
(Steady)
(Steady)
(Steady)
(Steady)
(Steady)
(Steady)

## Desktop Defects
Jan 17 Release
Defect # | Priority | Summary | Resolution Status | Regression Areas | QA Status | Comments
BBBSL-2100 | Severity/Priority P1 | Staging Issue | Resolved | Association with categories for collection products | In progress | QA Testing to be completed on Monday
BBBSL-2237 | Severity/Priority P2 | BazaarVoice Ratings on Certona carousels | Resolved | Ratings on certona carousels on all 6 concepts | Passed
BBBSL-2248 | Severity/Priority P2 | NPE at com.bbb.commerce.cart.droplet.CartRegistryInfoDroplet | Resolved | Cart- Adding bopus items in cart for anonymous user on desktop concepts | Passed
PS-17599 | Severity/Priority P2 | PS-17561 HeuristicMixedException exception in checkout | Resolved | checkout flow on all 6 concetps | Dev Testable | Cart and Checkout has been covered by QA
PS-18451 | Severity/Priority P2 | Fw: Baby Registrant Question | Resolved | Registry guest view on 3 desktop concepts | Passed
BBBSL-2080 | Severity/Priority P3 | Remove sapient copyright from mobile and desktop code | Resolved | Whole site on all 6 concepts | Dev Testable | Whole site sanity done by QA
BBBSL-2124 | Severity/Priority P4 | <br> tag is present in the error message of the Gift Card | Resolved | Checkout-Payment page on desktop concepts | Passed
WEB-254 | Severity/Priority P4 | Sales file extract taking 1 hour for Endeca full baseline | Resolved | Sales data feed - Endeca stored data extract | Passed

## Additonal Items (hidden)
December 7th Release
New dropdown taxonomy markup/CSS | Mandeep/Vijay
Seller registration number | Rajesh
- Keyboard Focus Indication All links have no focus indication because of "outline: 0 none;" Suggestion is to use same effect for hover as for focus (active) | Mandeep
Disable Inventory tab in BCC for QA and Production environments
Secure Cookie

## Mobile Defects
Jan 17 Release
Defect # | Priority | Title | Resolution Status | Regression Areas | QA Status | Comments
BSL-2234 | Severity/Priority P2 | Hotmail email subject has HTML content | Resolved | email a friend | Passed
BSL-2348 | Severity/Priority P2 | Mobile Web: All Concepts: Wedding Channel Pixel Failing | Resolved | wedding channel on registry confirmation/ order confirmation | Passed | This was patched on UAT east on 13th Jan
BSL-2349 | Severity/Priority P2 | Mobile Web: All Concepts: Bump Pixel Failing | Resolved | bump channel on registry confirmation/ order confirmation | Passed | This was patched on UAT east on 13th Jan
BSL-2145 | Severity/Priority P2 | Remove unused code from the Mobile site | Resolved | whole site | Dev Testable | QA regression testing done
BSL-2073 | Severity/Priority P3 | Default preffered shipping address is not selected while checkout as registered user | Resolved | My account-Preferred shipping adress on mobile concepts | Passed

## Known Issues
Jan 17 Release
JIRA Defect ID | Priority | Issue Description | Impacted Area | Comments
BSL-2388 | Severity/Priority P2 | Iphone 5 ¦ My account page is not fully loaded after account creation. | Mobile - My Account | This defect exists in productioin and will be fixed in next build
BSL-2389 | Severity/Priority P3 | Expanded Filter by options are not displaying in modal window | Mobile- Category filter | It is regression of fix BSL-1731 done by Ronald S Brown
BSL-2390 | Severity/Priority P4 | Phone Number label required instead of key. | Mobile- Create Registry | It is data packet miss for defect BSL-2339 done by Ronald S Brown