## Index
Summary
Date | 2014-07-08
Track | Application Support
Created by | Minhaj Siddiqui
Release Date | 2014-07-08
Release Number | 2.04.02.001
Location of EAR | /local1/atg/weblogic/application/bbb_prod/BBBStore.ear /local1/atg/weblogic/application/bbb_pub/BBBStore.ear /local1/atg/weblogic/application/bbb_stg/BBBStore.ear
Reviewed by | Imran Khan
Scope | JIRA Defects [Desktop Baby, Desktop BBB, Desktop Canada, Mobile Baby, Mobile BBB and Mobile Canada]
Prerequisite | July build - 2.04.02.001 packet-1 delivered on 23rd June must have been applied
(Steady)
(Steady)
(Steady)
(Steady)
(Steady)
(Steady)
(Steady)
(Steady)
(Steady)
(Steady)
(Steady)
(Steady)

## Additonal Items (hidden)
December 7th Release
New dropdown taxonomy markup/CSS | Mandeep/Vijay
Seller registration number | Rajesh
- Keyboard Focus Indication All links have no focus indication because of "outline: 0 none;" Suggestion is to use same effect for hover as for focus (active) | Mandeep
Disable Inventory tab in BCC for QA and Production environments
Secure Cookie

## Desktop Defects
July 08 Release
Defect # | Priority | Summary | Resolution Status | Regression Areas | QA Status | Comments
BBBSL-2848 | Severity/Priority 2 | CMPI Authenticate not getting triggered due to Ajax issues | Resolved | Credit Card verify by visa , Order checkout | Passed | This fix was sent as ps hot fix and should be validated in July PS as well
BBBSL-2859 | Severity/Priority 2 | order preview jsp is showing order number every time there is failure from centinal | Resolved | Order preview, Order Confirmation and Order Tracking Detail pages | Passed | This fix was sent as ps hot fix and should be validated in July PS as well
BBBSL-2862 | Severity/Priority 2 | Fix the logs of CMPI look up/authenticate request which is printing clear text credit card | Resolved | Validate checkout using verify by visa | Passed | This fix was sent as ps hot fix and should be validated in July PS as well
BBBSL-2657 | Severity/Priority 2 | Certona - item on Certona still with $0 pricing. | Resolved | Certona catalog feed for sku feed's pricing tag | Passed | Though this was sent in last july build packet but due to regression it got reopened. Please validate it again.
BBBSL-2839 | Severity/Priority 1 | Search "Sheets" results is not redirecting to incorrect URL with message "The page isn't redirecting properly" | Resolved | Search functionality on all concepts | Passed | This fix was sent as ps hot fix and should be validated in July PS as well
UAT-318 | Severity/Priority 2 | Brand Page URL- The old brand URLs are not working and can break the pages. The old brand URLs should continue to work Partial Search Logic – Strikethrough | Resolved | Test all Old & new brand page url | Not verified by Sapient QA | This fix was sent as ps hot fix and should be validated in July PS as well
UAT-314 | Severity/Priority 1 | Floating Node should not have "Categories" facet | Closed | Floating nodes should be visible | Not verified by Sapient QA | This fix was sent as ps hot fix and should be validated in July PS as well
UAT-308 | Severity/Priority 1 | Partial Matching - should not fire on partial searches | Resolved | Partial Matching Functionality | Not verified by Sapient QA | This fix was sent as ps hot fix and should be validated in July PS as well
UAT-326 | Severity/Priority 2 | 3DS: Modal - broken image | Resolved | Images on 3D secure model | Passed | This fix was sent as ps hot fix and should be validated in July PS as well
BBBSL-2597 | Severity/Priority 2 | Certona Catalog full feed taking almost 6 days to finish | Resolved | Certona catalog full feed | Not verified by Sapient QA
BBBSL-2507 | Severity/Priority 1 | Stored procedure extract for Endeca partial updates | Resolved | Endeca flat files for brands, product item attributes generation for partial SPs | Passed
BBBSL-2865 | Severity/Priority 2 | College Events need to be sorted by Start date of event | Resolved | College event page on US and CA sites | Passed | This fix was sent as ps hot fix and should be validated in July PS as well
BBBSL-2697 | Severity/Priority 1 | What's new L3's not tagged in Omniture on BBBY US & CA | Resolved | Omniture tags on PLP | Passed
PS-22659 | Severity/Priority 1 | Web 2.2: Some nodes (e.g., #12829) have incorrect canonical and x-default URLs | Resolved | Category canonical URLS in top CMS navigation for all 3 concepts of desktop | Passed | This fix was sent as ps hot fix and should be validated in July PS as well
BBBSL-2875 | Severity/Priority 2 | Omniture - evar1 and 46 when adding to registry before logging in | Resolved | Omniture call for add to registry functionality on PDP for guest user | Passed | This fix was sent as ps hot fix and should be validated in July PS as well
BBBSL-2854 | Severity/Priority 3 | Fix on Featured Products | Resolved | Featured products on Search results page , PLP and Brand Results page on all 3 concepts of desktop | Passed | This fix was sent as ps hot fix and should be validated in July PS as well
BBBSL-2866 | Severity/Priority 3 | Make code changes to decrease the default result set size to 30 for specific agents | Resolved | Search results page , PLP and Brands Results page on all 6 concpets | Passed | This fix was sent as ps hot fix and should be validated in July PS as well
BBBSL-2853 | Severity/Priority 3 | ThirdParty tag scope (On/Off) including removal of duplicate code from header and pagestart.jsp | Resolved | Perform high level sanity on all 3 concepts of desktop with Third Party Switch ON/OFF functionality | Passed | This fix was sent as ps hot fix and should be validated in July PS as well
BBBSL-2894 | Severity/Priority 4 | remove setting of config key attribute in request in TPSwitch Tag class | Resolved | Perform high level sanity on all 3 concepts of desktop with Third Party Switch ON/OFF functionality | Passed | This fix was sent as ps hot fix and should be validated in July PS as well
BSL-2469 | Severity/Priority 2 | Autoselect CC (m43/RM-18960) | Resolved | Add/Edit Credit card on Payment page & My Account | Passed

## Guided Selling
July 08 Release
Defect # | Priority | Summary | Resolution Status | Regression Areas | QA Status | Comments
UAT-317 | Severity/Priority 2 | FF2- Product Information is not displayed on FF2 Cart Email | Resolved | FF2 cart email | Not verified by SapientQA | This fix was sent as ps hot fix and should be validated in July PS as well

## Mobile Defects
July 08 Release
Defect # | Priority | Summary | Resolution Status | Regression Areas | QA Status | Comments
BSL-2056 | Severity/Priority 1 | Endeca Redirects - RM Defect # 20633 | Resolved | Baby mobile 2.0 Endeca redirects | Not verified by Sapient QA
UAT-327 | Severity/Priority 1 | Mobile Baby Order Confirmation Page broken for a specific scenario | Closed | Error functionality on Confirmation page | Passed | This fix was sent as ps hot fix and should be validated in July PS as well
UAT-108 | Severity/Priority 2 | #501-A1 Null Search Results - Redundant 'sorry' Messages | Resolved | The null search results page | Passed | This fix was sent as ps hot fix and should be validated in July PS as well
UAT-334 | Severity/Priority 2 | Incorrect Suggestions on clicking any brand or Shop by Brand – UI Misaligned ( eg Cabydor Brand ) | Resolved | UI Brand Detail Page | Passed | This fix was sent as ps hot fix and should be validated in July PS as well
BSL-2697 | Severity/Priority 1 | For CJ Mobile pixel - when an item is on clearance, the price passed through the pixel is the orginal price, not the clearance price | Resolved | CJ pixel firing on mobile on all 3 sites | Passed | This fix was sent as ps hot fix and should be validated in July PS as well
BSL-2410 | Severity/Priority 1 | CJ Pixel: Sending Order Amount before applying Coupons to CJ | Resolved | CJ pixel firing on mobile on all 3 sites | Passed | This fix was sent as ps hot fix and should be validated in July PS as well
BSL-2699 | Severity/Priority 1 | RKG Order Conversion Pixels have been removed from all mobile sites | Resolved | RKG pixel firing on mobile on all 3 sites | Passed | This fix was sent as ps hot fix and should be validated in July PS as well

## Known Issues
July 08 Release
JIRA Defect ID | Priority | Issue Description | Impacted Area | Comments