## Index
Summary
Date | 2014-07-14
Track | Application Support
Created by | Sanjay Kumar Sharma
Release Date | 2014-07-14
Release Number | 2.04.01.008
Location of EAR | /local1/atg/weblogic/application/bbb_prod/BBBStore.ear /local1/atg/weblogic/application/bbb_pub/BBBStore.ear /local1/atg/weblogic/application/bbb_stg/BBBStore.ear
Reviewed by
Scope | JIRA Defects [Desktop Baby, Desktop BBB, Desktop Canada, Mobile Baby, Mobile BBB and Mobile Canada]
Prerequisite | July build - 2.04.02.001 packet-1 delivered on 23rd June must have been applied
(Steady)
(Steady)
(Steady)
(Steady)
(Steady)
(Steady)
(Steady)
(Steady)
(Steady)
(Steady)
(Steady)
(Steady)

## Additonal Items (hidden)
December 7th Release
New dropdown taxonomy markup/CSS | Mandeep/Vijay
Seller registration number | Rajesh
- Keyboard Focus Indication All links have no focus indication because of "outline: 0 none;" Suggestion is to use same effect for hover as for focus (active) | Mandeep
Disable Inventory tab in BCC for QA and Production environments
Secure Cookie

## Desktop Defects
July 08 Release
Defect # | Priority | Summary | Resolution Status | Regression Areas | QA Status | Comments
PS-20624 | Severity/Priority 2 | Need RKG Dart Floodlight Tags added to College Site Pages | Resolved | College Landing Page | Passed | Fixed in July but need patch to be delivered this week
PS-22757 | Severity/Priority 1 | Clearance sort by redirect | Resolved | For Clearance & What's New Categories test all sort by options redirects | Passed
BBBSL-2907 | Severity/Priority 3 | Search page loading slow because we are checking for active/inactive property of product | Resolved | Search Page functioanlities on all the concepts | Passed
PS-22897 | Severity/Priority 4 | Cardinal issue - On load | Resolved | 3d-secure modal in VBV flow | Passed

## Guided Selling
July 08 Release
Defect # | Priority | Summary | Resolution Status | Regression Areas | QA Status | Comments
UAT-317 | Severity/Priority 2 | FF2- Product Information is not displayed on FF2 Cart Email

## Mobile Defects
July 08 Release
Defect # | Priority | Summary | Resolution Status | Regression Areas | QA Status | Comments

## Known Issues
July 08 Release
JIRA Defect ID | Priority | Issue Description | Impacted Area | Comments