## Index
Summary
Date | 2014-04-24
Track | Application Support
Created by | Sachin Sharma
Release Date | 2014-04-24
Release Number | 2.03.04.001
Location of EAR | /local1/atg/weblogic/application/bbb_prod/BBBStore.ear /local1/atg/weblogic/application/bbb_pub/BBBStore.ear /local1/atg/weblogic/application/bbb_stg/BBBStore.ear
Reviewed by
Scope | JIRA Defects [Desktop Baby, Desktop BBB, Desktop Canada, Mobile Baby, Mobile BBB and Mobile Canada]
Prerequisite | April build - 2.03.03.001 must have been applied
(Steady)
(Steady)
(Steady)
(Steady)
(Steady)
(Steady)
(Steady)
(Steady)
(Steady)
(Steady)
(Steady)
(Steady)

## Additonal Items (hidden)
December 7th Release
New dropdown taxonomy markup/CSS | Mandeep/Vijay
Seller registration number | Rajesh
- Keyboard Focus Indication All links have no focus indication because of "outline: 0 none;" Suggestion is to use same effect for hover as for focus (active) | Mandeep
Disable Inventory tab in BCC for QA and Production environments
Secure Cookie

## Desktop Defects
April 24 Release
Defect # | Priority | Summary | Status | Regression Areas | QA Status | Comments
Defect # | Priority | Summary | Resolution Status | Regression Areas | QA Status | Comments
BBBSL-2533 | Severity/Priority 4 | Make favorite store button shaking on find a store page | Resolved | Verify Find store functionality and check the results | Not validated
BBBSL-2532 | Severity/Priority 3 | create account page ¦ Tag is comming with cancel button | Resolved | Create account page | Not validated
BBBSL-2442 | Severity/Priority 3 | Add Pre-Tax Total to Shipping & Billing Pages | Resolved | Check Order Summary dialog box in top right corner on Shipping and billing pages | Not validated
BBBSL-1532 | Severity/Priority 1 | PDP redirect issue | Resolved | Redirection from Legacy product details page to new site's PDP page. Browse PDP page. | Not validated
BBBSL-2353 | Severity/Priority 2 | Adoptions Checklists | Resolved | Verify left navigation of static registry pages on baby site. | Not validated
PS-19138 | Severity/Priority 1 | Certona - there are 2 calls on the pdp for the add to registry | Resolved | Add item to registry from PDP. Certona call for the PDP page should be work fine. | Not validated
BBBSL-2440 | Severity/Priority 3 | In Canada Store locator check the display online flag before rendering on web. | Resolved | Verify Canada store locator page | Not validated
BBBSL-2280 | Severity/Priority 2 | Omniture - out of stock functionality does not work for sku level | Resolved | Verify Out of stock product on PDP page in following scenarios 1.Normal product 2.collection product 3.Accessories product | Not validated
PS-20072 | Severity/Priority 1 | Create the Perfect Registry option appearing for Skedge.me test stores | Resolved | Create Registry page and Registry Confirmation page | DEV TESTABLE
BBBSL-2193 | Severity/Priority 1 | Inclusion Functionality for Promotions | Resolved | For Both Mobile & Desktop : Applying coupons on Bopus Order Applying coupons on Normal Order Applying coupons on Hybrid Order Checking total discount amount after applying item level inclusive coupon on the items which are included. Checking total discount amount after applying order level inclusive coupon on the order having items which are included. | Not verified by Sapient QA
BBBSL-2635 | Severity/Priority 2 | College Name not dispalyed in order confirmation email in case of Bedding Kit and Weblink Order | Resolved | Order confirmation email for CBK and CWK orders, checkout functionality | QA Passed
BBBSL-2497 | Severity/Priority 2 | Exception when prefferred store-id is not set in registry | Resolved | Find in Store/Pickup in Store from Product detail page, cart page, registry owner page, Shipping Page and then Checkout using the Bopus item. | DEV TESTABLE
GS-154 | Severity/Priority 2 | Endeca Failing in SD BBB_SWITCH_A Schema | Resolved | 1) Guided Selling Endeca files generation taking place at all 3 schemas. 2) Log Messages captured in Process_Support table. 3) Guided Selling Endeca Baseline working fine. | Not verified by Sapient QA
BBBSL-1525 | Severity/Priority 3 | Add UPS Return Label to CAN site | Resolved | Form submission on easy returns page on all three sites on dekstop | DEV TESTABLE | Can not verify at front end
BBBSL-2449 | Severity/Priority 3 | BBB2594080741 -- Tax of Item w/ Coupon | Resolved | 1)- cart page,coupon page,couponDisplay page when coupon is selected in a new tab,tax is should be calcuted on the discount price. | QA Passed
CM-9843 | Severity/Priority 3 | Please delete the following brands | Resolved | 1) Regression areas are the PDP page where brand association and disassociation is listed for a product on all 3 sites of desktop and mobile. 2)PIM Feed import job for product brand association. 3) PLP page 4) Brand Listing Page. | Not verified by Sapient QA
BBBSL-2516 | Severity/Priority 3 | Website Issue | Resolved | 1)Findyourcollege,FindInStore page -While passing the parameter address in city and city in address. | QA Passed
BBBSL-2587 | Severity/Priority 3 | Refresh language on Mobile Null Search Results page | Resolved | Search Result Page | QA Passed

## Mobile Defects
April 24 Release
Defect # | Priority | Title | Status | Regression Areas | QA Status | Comments
BSL-2547 | Severity/Priority 1 | BSL-2480 Account Extension Popup on Create Account Page | Resolved | 1) User Registration Funtionality 2) Login Functionality 3) Account Page Test for both mobile and desktop | QA Passed
BSL-2548 | Severity/Priority 1 | BSL-2480 Account Extension Popup on Order Confirmation Page | Resolved | 1) User Registration Funtionality 2) Login Functionality 3) Account Page Test for both mobile and desktop | QA Passed
BSL-2550 | Severity/Priority 1 | BSL-2480 Account Migration Popup on Create Account Page and Order Confirmation Page | Resolved | 1) User Registration Funtionality 2) Login Functionality 3) Account Page Test for both mobile and desktop | QA Passed
BSL-2480 | Severity/Priority 1 | Extend Sister Store Account (m2) | Resolved | 1) User Registration Funtionality 2) Login Functionality 3) Reset Password functionality. Test for both mobile and desktop | QA Passed
BSL-2059 | Severity/Priority 1 | Trying to add shipping address modal does not scroll and user cannot navigate to address fields | Resolved | checkout Shipping Address section | DEV TESTABLE
BSL-2549 | Severity/Priority 1 | BSL-2480 Update checkForRegistration Rest service for Account extension and migration | Resolved | 1) User Registration Funtionality 2) Login Functionality 3) Account Page 3) Reset Password functionality. Test for both mobile and desktop | QA Passed
BSL-1970 | Severity/Priority 2 | Certona - category pages are not tagged | Resolved | 1) Check for Certona Res-x call for L2 and L3 catregory on all the mobile sites. | Not verified by Sapient QA
BSL-2418 | Severity/Priority 2 | Error, Displaying "did you mean..." on BBBY & Baby Mobile Site Search | Resolved | Search Result Page | QA Passed
BSL-2554 | Severity/Priority 3 | Use as billing address checkbox is not displayed on navigating to shipping page from cart | Resolved | checkout Shipping Address section | QA Passed
BSL-2516 | Severity/Priority 4 | Search Registry page throws internal server error in UAT East | Resolved | 1)Findyourcollege,FindInStore page -While passing the parameter address in city and city in address. | QA Passed

## Known Issues
April 24 Release
JIRA Defect ID | Priority | Issue Description | Impacted Area | Comments
BBBSL-2645 | Severity/Priority 3 | Mini cart promotion label missing. | Mini Cart